## PARTNERS
PARTNERS' LIST
# | City name | Short Name | Country | Development Level | Region | Daily Staff Rate (EUR) | ERDF
LP | Eindhoven | EIN | NL | More developed | West | 360 | 65%
P2 | Aarhus | AAR | DK | More developed | North | 290 | 65%
P3 | Cartagena | CAR | ES | Transition region | South | 180 | 70%
P4 | Gdańsk | GDA | PL | Less developed | East | 150 | 80%
P5 | Iași | IAS | RO | Less developed | East | 180 | 80%
P6 | Veszprém | VES | HU | Less developed | East | 120 | 80%
P7 | Oulu | OUL | FI | Transition region | North | 250 | 70%
P8 | Perugia | PER | IT | Transition region | South | 180 | 70%
P9 | Тetovo | TET | MK | IPA | IPA | 85 | 95%
P10 | Viladecans | VIL | ES | More developed | South | 180 | 65%

## IMPLEMENTATION
IMPLEMENTATION PLAN
Action | Activity | Partner in charge | Participating | Output | ACTIVATION | [6 empty] | PLANNING ACTIONS | [11 empty] | PREPARING IMPLEMENTATION | [8 empty] | FINALE
[5 empty] | 2023 | [6 empty] | 2024 | [11 empty] | 2025
[5 empty] | Q1 |  |  | Q2 |  |  |  | Q3 |  |  | Q4 |  |  | Q5 |  |  | Q6 |  |  | Q7 |  |  | Q8 |  |  | Q9 |  |  | Q10
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[5 empty] | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination
1.1.1 | Signature of the Subsidy Contract | LP |  | Subsidy Contract signed | bar: Q1 1 J
1.1.2 | Signature of the Joint Convention | LP | All PPs | Joint Convention signed | bar: Q1 1 J to Q1 2 J
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 10 team set up | bar: Q1 1 J to Q1 3 A
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 3 Expert Request Forms | bar: Q1 1 J to Q10 31 D
1.1.5
1.2 | Coordination meetings and mid-term reflection
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 10 personal meetings | bar: Q1 2 J; Q2 6 N; Q3 9 F; Q4 11 A; Q5 16 S; Q6 18 N; Q7 21 F; Q8 24 M; Q9 27 A; Q10 30 N
1.2.2 | Online coordination meetings | LP/LE | All PPs | 10 online meetings | bar: Q1 1 J; Q2 5 O; Q3 8 J; Q3 10 M; Q5 15 A; Q6 17 O; Q7 20 J; Q8 23 A; Q9 26 J; Q10 29 O
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 Reflection | bar: Q6 18 N to Q6 19 D
1.2.4
1.2.5
1.3 | Reporting and project closure
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 3 FLC certificates per partner
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 3 joint reports
1.3.3 | Closure Report | LP | All PPs | 1 Closure Report | bar: Q10 30 N to Q10 31 D
1.3.4
1.3.5
WP2 | TRANSNATIONAL ACTIVITIES
2.1 | Transnational Activities
2.1.1 | Programme level kick-off meeting | All PPs |  | Participation of 10 cities | bar: Q1 1 J
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 10 city visists + 1 Network Roadmap | bar: Q2 4 S to Q2 6 N
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 1 Transnational Meeting | bar: Q1 2 J
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 1 Transnational Meeting | bar: Q2 6 N
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 1 Transnational Meeting | bar: Q3 9 F
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 1 Transnational Meeting | bar: Q4 12 M
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 1 Transnational Meeting | bar: Q5 16 S
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 1 Transnational Meeting | bar: Q6 18 N
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 1 Transnational Meeting | bar: Q7 22 M
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 1 Transnational Meeting | bar: Q8 24 M
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 1 Transnational Meeting | bar: Q9 28 S
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 1 Transnational Meeting | bar: Q10 30 N
2.1.13 | Staff Exchanges |  | All PPs | 2 staff members travelling to another city | bar: Q3 9 F; Q4 12 M; Q5 16 S; Q6 18 N; Q7 21 F; Q8 24 M; Q9 28 S; Q10 30 N
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 Quarterly Network Reports, 1 Good Practice Catalogue | bar: Q3 10 M; Q4 13 J; Q5 16 S; Q6 19 D; Q8 23 A; Q8 25 J; Q10 30 N
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | Participation of 10 cities (max. 2 persons) | bar: Q1 3 A
2.2 | Transnational communication
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 Plan, 1 logo | bar: Q2 4 S to Q2 6 N
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 Acronym, 1 tagline, 1 boilerplate | bar: Q1 1 J to Q1 2 J
2.2.3 | A3 poster (?) | LP/LE | All PPs | 10 posters | bar: Q2 4 S to Q2 5 O
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 sites edited | bar: Q2 6 N
2.2.5 | Editing the project website | LP/LE | All PPs | Monthly updates | bar: Q2 6 N
2.2.6 | Network Articles | LE | All PPs | 3 articles by LE | bar: Q2 6 N; Q6 19 D; Q10 30 N
2.2.7 | Network Results Product | LP/LE | All PPs | 1 thematic study | bar: Q10 29 O to Q10 30 N
2.2.8 | Final Conference |  | All PPs | 1 Final conference (as part of TNM10) | bar: Q10 30 N
2.2.9
2.2.10
2.2.11
2.2.12
2.2.13
2.2.14
2.2.15
WP3 | LOCAL ACTIVITIES
3.1 | Operation of the ULG
3.1.1 | Setting up the ULG | All PPs | LE/LP | 1 ULG per city set up | bar: Q1 1 J to Q1 3 A
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 1 team building per ULG | bar: Q1 3 A
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 10 ULG coordinators selected | bar: Q1 1 J to Q1 2 J
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | min. 8 ULG meetings per partner | bar: Q3 8 J; Q4 11 A; Q5 14 J; Q6 17 O; Q7 20 J; Q8 23 A; Q9 26 J; Q10 29 O
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 5*10 Learning Needs identified | bar: Q2 4 S to Q2 6 N
3.1.6 | Learning Grids created | All PPs | LE/LP | 1 Learning Grid | bar: Q2 4 S to Q2 6 N
3.1.7 | Learning Log | All PPs | LE/LP | 1 Learning Log
3.1.8
3.2 | Small Scale Actions
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 1 SSA Plan per each city | bar: Q3 10 M to Q5 14 J
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 1 SSA carried out per city | bar: Q4 13 J to Q8 23 A
3.2.3
3.3 | Preparation of the Integrated Action Plans
3.3.1 | Draft IAP | All PPs | LE/LP | 1 Draft IAP per city | bar: Q6 18 N to Q7 20 J
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 1 Final IAP per city | bar: Q9 26 J to Q9 28 S
3.3.3
3.4 | Local level communication
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 10 Local Visual Identities | bar: Q1 3 A to Q2 4 S
3.4.2 | Setting up online presence (social media) | All PPs | LP | 10 social media account created | bar: Q2 6 N
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | Monthly updates | bar: Q2 6 N; Q3 9 F; Q4 12 M; Q5 15 A; Q6 18 N; Q7 21 F; Q8 24 M; Q9 27 A; Q10 30 N
3.4.4 | Videos from staff exchanges | All PPs | LP | 1 per PP | bar: Q2 6 N; Q3 10 M; Q4 13 J; Q6 17 O; Q6 19 D; Q7 22 M; Q8 25 J; Q9 28 S; Q10 30 N
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 participation in a national event | bar: Q10 30 N
3.4.6 | Local IAP dissemination events | All PPs | LP | 1 event | bar: Q10 29 O to Q10 31 D
3.4.7
3.4.8

## STAFF_DAYS
STAFF DAYS
Action | Activity | Partner in charge | Participating | LP | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | TOTAL | LP | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | TOTAL
|  |  |  | NL | DK | ES | PL | RO | HU | FI | IT | MK | ES |  | NL | DK | ES | PL | RO | HU | FI | IT | MK | ES
|  |  |  | Eindhoven | Aarhus | Cartagena | Gdańsk | Iași | Veszprém | Oulu | Perugia | Тetovo | Viladecans |  | Eindhoven | Aarhus | Cartagena | Gdańsk | Iași | Veszprém | Oulu | Perugia | Тetovo | Viladecans
|  |  |  | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180
|  |  |  | EIN | AAR | CAR | GDA | IAS | VES | OUL | PER | TET | VIL |  | EIN | AAR | CAR | GDA | IAS | VES | OUL | PER | TET | VIL
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 21 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 102 | 7560 | 2610 | 1620 | 1350 | 1620 | 1080 | 2250 | 1620 | 765 | 1620 | 22095
1.1.1 | Signature of the Subsidy Contract | LP | [11 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
1.1.2 | Signature of the Joint Convention | LP | All PPs | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 720 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 2335
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 20 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 360 | 3950
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 16 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 61 | 5760 | 1450 | 900 | 750 | 900 | 600 | 1250 | 900 | 425 | 900 | 13835
1.1.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Coordination meetings and mid-term reflection |  |  | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 31 | 1440 | 870 | 540 | 450 | 540 | 360 | 750 | 540 | 255 | 540 | 6285
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 20 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 360 | 3950
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 720 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 2335
1.2.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Reporting and project closure |  |  | 27 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 108 | 9720 | 2610 | 1620 | 1350 | 1620 | 1080 | 2250 | 1620 | 765 | 1620 | 24255
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 66 | 4320 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 1080 | 14010
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 30 | 4320 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 360 | 7550
1.3.3 | Closure Report | LP | All PPs | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1080 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 2695
1.3.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.5 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 52 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 241 | 18720 | 6090 | 3780 | 3150 | 3780 | 2520 | 5250 | 3780 | 1785 | 3780 | 52635
WP2 | TRANSNATIONAL ACTIVITIES
2.1 | Transnational Activities |  |  | 104 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 87 | 59 | 859 | 37440 | 25230 | 15660 | 13050 | 15660 | 10440 | 21750 | 15660 | 7395 | 10620 | 172905
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 39 | 1440 | 1160 | 720 | 600 | 720 | 480 | 1000 | 720 | 340 | 540 | 7720
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 12 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 38 | 4320 | 870 | 540 | 450 | 540 | 360 | 750 | 540 | 255 | 360 | 8985
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 78 | 2880 | 2320 | 1440 | 1200 | 1440 | 960 | 2000 | 1440 | 680 | 1080 | 15440
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.13 | Staff Exchanges |  | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 58 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 11490
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 62 | 3600 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 12930
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 62 | 3600 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 720 | 12930
2.2 | Transnational communication |  |  | 31 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 184 | 11160 | 4930 | 3060 | 2550 | 3060 | 2040 | 4250 | 3060 | 1445 | 3060 | 38615
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11 | 720 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 2335
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
2.2.3 | A3 poster (?) | LP/LE | All PPs | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 20 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 360 | 3950
2.2.5 | Editing the project website | LP/LE | All PPs | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 30 | 4320 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 360 | 7550
2.2.6 | Network Articles | LE | All PPs | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
2.2.7 | Network Results Product | LP/LE | All PPs | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 33 | 2160 | 870 | 540 | 450 | 540 | 360 | 750 | 540 | 255 | 540 | 7005
2.2.8 | Final Conference |  | All PPs | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 60 | 2160 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 1080 | 11850
2.2.9 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.10 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.11 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.12 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.13 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.14 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.15 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 135 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 104 | 76 | 1043 | 48600 | 30160 | 18720 | 15600 | 18720 | 12480 | 26000 | 18720 | 8840 | 13680 | 211520
WP3 | LOCAL ACTIVITIES
3.1 | Operation of the ULG |  |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 11 | 209 | 7920 | 6380 | 3960 | 3300 | 3960 | 2640 | 5500 | 3960 | 1870 | 1980 | 41470
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 19 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 180 | 3770
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 28 | 1080 | 870 | 540 | 450 | 540 | 360 | 750 | 540 | 255 | 180 | 5565
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 76 | 2880 | 2320 | 1440 | 1200 | 1440 | 960 | 2000 | 1440 | 680 | 720 | 15080
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 19 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 180 | 3770
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 19 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 180 | 3770
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 38 | 1440 | 1160 | 720 | 600 | 720 | 480 | 1000 | 720 | 340 | 360 | 7540
3.1.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Small Scale Actions |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 38 | 1440 | 1160 | 720 | 600 | 720 | 480 | 1000 | 720 | 340 | 360 | 7540
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 19 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 180 | 3770
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 19 | 720 | 580 | 360 | 300 | 360 | 240 | 500 | 360 | 170 | 180 | 3770
3.2.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 95 | 3600 | 2900 | 1800 | 1500 | 1800 | 1200 | 2500 | 1800 | 850 | 900 | 18850
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 48 | 1800 | 1450 | 900 | 750 | 900 | 600 | 1250 | 900 | 425 | 540 | 9515
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 47 | 1800 | 1450 | 900 | 750 | 900 | 600 | 1250 | 900 | 425 | 360 | 9335
3.3.3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 | Local level communication |  |  | 38 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 146 | 13680 | 3480 | 2160 | 1800 | 2160 | 1440 | 3000 | 2160 | 1020 | 2160 | 33060
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
3.4.2 | Setting up online presence (social media) | All PPs | LP | [10 empty] | 10 | 360 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 1975 | bar: EIN to VIL
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 30 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 84 | 10800 | 1740 | 1080 | 900 | 1080 | 720 | 1500 | 1080 | 510 | 1080 | 20490
3.4.4 | Videos from staff exchanges | All PPs | LP | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 1080 | 290 | 180 | 150 | 180 | 120 | 250 | 180 | 85 | 180 | 2695
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 30 | 1080 | 870 | 540 | 450 | 540 | 360 | 750 | 540 | 255 | 540 | 5925
3.4.7 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 74 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 30 | 488 | 26640 | 13920 | 8640 | 7200 | 8640 | 5760 | 12000 | 8640 | 4080 | 5400 | 100920
|  |  |  | 261 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 127 | 1772 | 93960 | 50170 | 31140 | 25950 | 31140 | 20760 | 43250 | 31140 | 14705 | 22860 | 365075

## SUMMARY
ERDF
# | City name | Short Name | Country | FORECASTED TOTAL BUDGET | % ERDF | FORECASTED ERDF | FORECASTED cofinancing
LP | Eindhoven | EIN | NL | 203858 | 65% | 132507.7 | 71350.3
P2 | Aarhus | AAR | DK | 94478.5 | 65% | 61411.025 | 33067.475
P3 | Cartagena | CAR | ES | 74197 | 70% | 51937.9 | 22259.1
P4 | Gdańsk | GDA | PL | 63347.5 | 80% | 50678 | 12669.5
P5 | Iași | IAS | RO | 68697 | 80% | 54957.6 | 13739.4
P6 | Veszprém | VES | HU | 62289 | 80% | 49831.2 | 12457.8
P7 | Oulu | OUL | FI | 87512.5 | 70% | 61258.75 | 26253.75
P8 | Perugia | PER | IT | 70997 | 70% | 49697.9 | 21299.1
P10 | Viladecans | VIL | ES | 75283 | 65% | 48933.95 | 26349.05
SUB-TOTAL |  |  |  | 800659.5 |  | 561214.025 | 239445.475
IPA
# | City name | Short Name | Country | FORECASTED TOTAL BUDGET | % IPA | FORECASTED IPA | FORECASTED cofinancing
P9 | Тetovo | TET | MK | 49340.25 | 95% | 46873.2375 | 2467.0125
SUB-TOTAL |  |  |  | 49340.25 |  | 46873.2375 | 2467.0125
TOTAL BUDGET
# | City name | Short Name | Country | FORECASTED TOTAL BUDGET | % ERDF | FORECASTED ERDF | FORECASTED cofinancing
WHOLE PARTNERSHIP TOTAL |  |  |  | 849999.75 |  | 608087.2625 | 241912.4875
ERDF PER YEAR
ERDF per year |  |  |  | FORECASTED ERDF
2023 |  |  |  | 168478.625
2024 |  |  |  | 157352.075
2025 |  |  |  | 235383.325
SUB-TOTAL |  |  |  | 561214.025
IPA PER YEAR
IPA per year |  |  |  | FORECASTED IPA
2023 |  |  |  | 12609.2075
2024 |  |  |  | 9963.0775
2025 |  |  |  | 24300.9525
SUB-TOTAL |  |  |  | 46873.2375

## TOTAL_BUDGET
| TOTAL BUDGET | [5 empty] | Total Budget |  |  |  | 849999.75 | 2023 | [5 empty] | Budget 2023 | 255402.15 | 2024 | [5 empty] | Budget 2024 | 233830.55 | 2025 | [5 empty] | Budget 2025 | 360767.05 | OK
[7 empty] | ERDF |  |  |  | 608087.2625 | [6 empty] | ERDF | 181087.8325 | [6 empty] | ERDF | 167315.1525 | [6 empty] | ERDF | 259684.2775 | OK
[7 empty] | National Co-financing |  |  |  | 241912.4875 | [6 empty] | Nat. Co-fin | 74314.3175 | [6 empty] | Nat. Co-fin | 66515.3975 | [6 empty] | Nat. Co-fin | 101082.7725 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 21 | 22095 | 1104.75 | 0 |  | 0 | 0 | 23199.75 | 9 | 11315 | 565.75 | 0 |  | 0 | 0 | 11880.75 | 2250 | 5390 | 269.5 | 0 |  | 0 | 0 | 5659.5 | 0 | 5390 | 269.5 | 0 |  | 0 | 0 | 5659.5 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 11 | 2335 | 116.75 | 0 |  | 0 | 0 | 2451.75 | 11 | 2335 | 116.75 | 0 |  | 0 | 0 | 2451.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 61 | 13835 | 691.75 | 0 |  | 0 | 0 | 14526.75 | 13 | 3055 | 152.75 | 0 |  | 0 | 0 | 3207.75 | 24 | 5390 | 269.5 | 0 |  | 0 | 0 | 5659.5 | 24 | 5390 | 269.5 | 0 |  | 0 | 0 | 5659.5 | OK
1.1.5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 4 | 6285 | 314.25 | 0 |  | 0 | 0 | 6599.25 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 750 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 4310 | 215.5 | 0 |  | 0 | 0 | 4525.5 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 11 | 2335 | 116.75 | 0 |  | 0 | 0 | 2451.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 11 | 2335 | 116.75 | 0 |  | 0 | 0 | 2451.75 | OK
1.2.4 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.3 | Reporting and project closure |  |  | 27 | 24255 | 1212.75 | 0 |  | 53500 | 0 | 78967.75 | 9 | 6470 | 323.5 | 0 |  | 10500 | 0 | 17293.5 | 2250 | 8085 | 404.25 | 0 |  | 21500 | 0 | 29989.25 | 0 | 9700 | 485 | 0 |  | 21500 | 0 | 31685 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 66 | 14010 | 700.5 | 0 |  | 25500 | 0 | 40210.5 | 22 | 4670 | 233.5 | 0 |  | 6500 | 0 | 11403.5 | 22 | 4670 | 233.5 | 0 |  | 9500 | 0 | 14403.5 | 22 | 4670 | 233.5 | 0 |  | 9500 | 0 | 14403.5 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 30 | 7550 | 377.5 | 0 |  | 28000 | 0 | 35927.5 | 4 | 1440 | 72 | 0 |  | 4000 | 0 | 5512 | 13 | 3055 | 152.75 | 0 |  | 12000 | 0 | 15207.75 | 13 | 3055 | 152.75 | 0 |  | 12000 | 0 | 15207.75 | OK
1.3.3 | Closure Report | LP | All PPs | 12 | 2695 | 134.75 | 0 |  | 0 | 0 | 2829.75 | 1 | 360 | 18 | 0 |  | 0 | 0 | 378 | 1 | 360 | 18 | 0 |  | 0 | 0 | 378 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | OK
1.3.4 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
|  |  |  | 52 | 52635 | 2631.75 | 0 |  | 53500 | 0 | 108766.75 | 21 | 17785 | 889.25 | 0 |  | 10500 | 0 | 29174.25 | 5250 | 15450 | 772.5 | 0 |  | 21500 | 0 | 37722.5 | 0 | 19400 | 970 | 0 |  | 21500 | 0 | 41870 | OK
WP2 | TRANSNATIONAL ACTIVITIES | [34 empty] | OK
2.1 | Transnational Activities |  |  | 104 | 172905 | 8645.25 | 125551 |  | 146180 | 0 | 453281.25 | 59 | 60335 | 3016.75 | 59600 |  | 43108 | 0 | 166059.75 | 21750 | 56375 | 2818.75 | 25450 |  | 48966 | 0 | 133609.75 | 0 | 56195 | 2809.75 | 40501 |  | 54106 | 0 | 153611.75 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 39 | 7720 | 386 | 0 |  | 0 | 0 | 8106 | 39 | 7720 | 386 | 0 |  | 0 | 0 | 8106 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 38 | 8985 | 449.25 | 3500 |  | 7600 | 0 | 20534.25 | 38 | 8985 | 449.25 | 3500 |  | 7600 | 0 | 20534.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 78 | 15440 | 772 | 15500 |  | 15900 | 0 | 47612 | 78 | 15440 | 772 | 15500 |  | 15900 | 0 | 47612 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 58 | 11490 | 574.5 | 18600 |  | 17100 | 0 | 47764.5 | 58 | 11490 | 574.5 | 18600 |  | 17100 | 0 | 47764.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 58 | 11490 | 574.5 | 10950 |  | 14350 | 0 | 37364.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 10950 |  | 14350 | 0 | 37364.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 58 | 11490 | 574.5 | 4750 |  | 10550 | 0 | 27364.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 4750 |  | 10550 | 0 | 27364.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 58 | 11490 | 574.5 | 5050 |  | 11050 | 0 | 28164.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 5050 |  | 11050 | 0 | 28164.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 58 | 11490 | 574.5 | 4700 |  | 11000 | 0 | 27764.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 4700 |  | 11000 | 0 | 27764.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 58 | 11490 | 574.5 | 11550 |  | 16650 | 0 | 40264.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 11550 |  | 16650 | 0 | 40264.5 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 58 | 11490 | 574.5 | 6400 |  | 11800 | 0 | 30264.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 6400 |  | 11800 | 0 | 30264.5 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 58 | 11490 | 574.5 | 15800 |  | 13600 | 0 | 41464.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 15800 |  | 13600 | 0 | 41464.5 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 58 | 11490 | 574.5 | 6751 |  | 10040 | 0 | 28855.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 58 | 11490 | 574.5 | 6751 |  | 10040 | 0 | 28855.5 | OK
2.1.13 | Staff Exchanges |  | All PPs | 58 | 11490 | 574.5 | 0 |  | 0 | 0 | 12064.5 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 62 | 12930 | 646.5 | 0 |  | 5040 | 0 | 18616.5 | 0 | 0 | 0 | 0 |  | 1008 | 0 | 1008 | 31 | 6465 | 323.25 | 0 |  | 2016 | 0 | 8804.25 | 31 | 6465 | 323.25 | 0 |  | 2016 | 0 | 8804.25 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 62 | 12930 | 646.5 | 22000 |  | 1500 | 0 | 37076.5 | 62 | 12930 | 646.5 | 22000 |  | 1500 | 0 | 37076.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2 | Transnational communication |  |  | 31 | 38615 | 1930.75 | 0 |  | 10000 | 0 | 50545.75 | 17 | 15265 | 763.25 | 0 |  | 6000 | 0 | 22028.25 | 4250 | 3055 | 152.75 | 0 |  | 2000 | 0 | 5207.75 | 0 | 20295 | 1014.75 | 0 |  | 2000 | 0 | 23309.75 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 11 | 2335 | 116.75 | 0 |  | 5000 | 0 | 7451.75 | 11 | 2335 | 116.75 | 0 |  | 5000 | 0 | 7451.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 20 | 3950 | 197.5 | 0 |  | 0 | 0 | 4147.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 30 | 7550 | 377.5 | 0 |  | 0 | 0 | 7927.5 | 22 | 4670 | 233.5 | 0 |  | 0 | 0 | 4903.5 | 4 | 1440 | 72 | 0 |  | 0 | 0 | 1512 | 4 | 1440 | 72 | 0 |  | 0 | 0 | 1512 | OK
2.2.6 | Network Articles | LE | All PPs | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 1 | 360 | 18 | 0 |  | 0 | 0 | 378 | 9 | 1615 | 80.75 | 0 |  | 0 | 0 | 1695.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 33 | 7005 | 350.25 | 0 |  | 5000 | 0 | 12355.25 | 0 | 0 | 0 | 0 |  | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 |  | 2000 | 0 | 2000 | 33 | 7005 | 350.25 | 0 |  | 2000 | 0 | 9355.25 | OK
2.2.8 | Final Conference |  | All PPs | 60 | 11850 | 592.5 | 0 |  | 0 | 0 | 12442.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 60 | 11850 | 592.5 | 0 |  | 0 | 0 | 12442.5 | OK
2.2.9 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
|  |  |  | 135 | 211520 | 10576 | 125551 |  | 156180 | 0 | 503827 | 76 | 75600 | 3780 | 59600 |  | 49108 | 0 | 188088 | 26000 | 59430 | 2971.5 | 25450 |  | 50966 | 0 | 138817.5 | 0 | 76490 | 3824.5 | 40501 |  | 56106 | 0 | 176921.5 | OK
WP3 | LOCAL ACTIVITIES | [34 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 41470 | 2073.5 | 0 |  | 36980 | 0 | 80523.5 | 11 | 26390 | 1319.5 | 0 |  | 1980 | 0 | 29689.5 | 5500 | 7540 | 377 | 0 |  | 17500 | 0 | 25417 | 0 | 7540 | 377 | 0 |  | 17500 | 0 | 25417 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 28 | 5565 | 278.25 | 0 |  | 0 | 0 | 5843.25 | 28 | 5565 | 278.25 | 0 |  | 0 | 0 | 5843.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 10 | 1975 | 98.75 | 0 |  | 19800 | 0 | 21873.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 9900 | 0 | 9900 | 0 | 0 | 0 | 0 |  | 9900 | 0 | 9900 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 76 | 15080 | 754 | 0 |  | 15200 | 0 | 31034 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 38 | 7540 | 377 | 0 |  | 7600 | 0 | 15517 | 38 | 7540 | 377 | 0 |  | 7600 | 0 | 15517 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 38 | 7540 | 377 | 0 |  | 1980 | 0 | 9897 | 38 | 7540 | 377 | 0 |  | 1980 | 0 | 9897 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 7540 | 377 | 0 |  | 60360 | 20000 | 88277 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1000 | 7540 | 377 | 0 |  | 360 | 0 | 8277 | 0 | 0 | 0 | 0 |  | 60000 | 20000 | 80000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 19 | 3770 | 188.5 | 0 |  | 360 | 0 | 4318.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 19 | 3770 | 188.5 | 0 |  | 360 | 0 | 4318.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 19 | 3770 | 188.5 | 0 |  | 60000 | 20000 | 83958.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 19 | 3770 | 188.5 | 0 |  | 0 | 0 | 3958.5 | 0 | 0 | 0 | 0 |  | 60000 | 20000 | 80000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 18850 | 942.5 | 0 |  | 4100 | 0 | 23892.5 | 5 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2500 | 9515 | 475.75 | 0 |  | 0 | 0 | 9990.75 | 0 | 9335 | 466.75 | 0 |  | 4100 | 0 | 13901.75 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 48 | 9515 | 475.75 | 0 |  | 0 | 0 | 9990.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 48 | 9515 | 475.75 | 0 |  | 0 | 0 | 9990.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 47 | 9335 | 466.75 | 0 |  | 4100 | 0 | 13901.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 47 | 9335 | 466.75 | 0 |  | 4100 | 0 | 13901.75 | OK
3.3.3 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.4 | Local level communication |  |  | 38 | 33060 | 1653 | 0 |  | 10000 | 0 | 44713 | 12 | 8048 | 402.4 | 0 |  | 0 | 0 | 8450.4 | 3000 | 8196 | 409.8 | 0 |  | 5000 | 0 | 13605.8 | 0 | 16816 | 840.8 | 0 |  | 5000 | 0 | 22656.8 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 10 | 1975 | 98.75 | 0 |  | 0 | 0 | 2073.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 84 | 20490 | 1024.5 | 0 |  | 0 | 0 | 21514.5 | 16.8 | 4098 | 204.9 | 0 |  | 0 | 0 | 4302.9 | 33.6 | 8196 | 409.8 | 0 |  | 0 | 0 | 8605.8 | 33.6 | 8196 | 409.8 | 0 |  | 0 | 0 | 8605.8 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 | 0 |  | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 |  | 5000 | 0 | 5000 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 12 | 2695 | 134.75 | 0 |  | 0 | 0 | 2829.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 12 | 2695 | 134.75 | 0 |  | 0 | 0 | 2829.75 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 30 | 5925 | 296.25 | 0 |  | 0 | 0 | 6221.25 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 30 | 5925 | 296.25 | 0 |  | 0 | 0 | 6221.25 | OK
3.4.7 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | OK
|  |  |  | 74 | 100920 | 5046 | 0 |  | 111440 | 20000 | 237406 | 30 | 34438 | 1721.9 | 0 |  | 1980 | 0 | 38139.9 | 12000 | 32791 | 1639.55 | 0 |  | 22860 | 0 | 57290.55 | 0 | 33691 | 1684.55 | 0 |  | 86600 | 20000 | 141975.55 | OK
|  |  |  | 261 | 365075 | 18253.75 | 125551 |  | 321120 | 20000 | 849999.75 | 173 | 127823 | 6391.15 | 59600 |  | 61588 | 0 | 255402.15 | 31140 | 107671 | 5383.55 | 25450 |  | 95326 | 0 | 233830.55 | 0 | 129581 | 6479.05 | 40501 |  | 164206 | 20000 | 360767.05 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 365075 | 127823 | 107671 | 129581 |  | OK
|  | Total |  | 365075 | 127823 | 107671 | 129581 |  | OK
| Office and Admin | Office and Administration |  | 18253.75 | 6391.15 | 5383.55 | 6479.05 |  | OK
|  | Total |  | 18253.75 | 6391.15 | 5383.55 | 6479.05 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 125551 | 59600 | 25450 | 40501 |  | OK
|  | Total |  | 125551 | 59600 | 25450 | 40501 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 104480 | 7988 | 16376 | 80116 |  | OK
|  | Ext. Meeting Organisation |  | 97000 | 16000 | 41500 | 39500 |  | OK
|  | Ext. Communication |  | 20000 | 6000 | 7000 | 7000 |  | OK
|  | Exp. & non-staff Travel |  | 79140 | 26100 | 22950 | 30090 |  | OK
|  | First Level Control |  | 20500 | 5500 | 7500 | 7500 |  | OK
|  | Total |  | 321120 | 61588 | 95326 | 164206 |  | OK
| Equipment | Equipment |  | 20000 | 0 | 0 | 20000 |  | OK
|  | Total |  | 20000 | 0 | 0 | 20000 |  | OK
| TOTAL |  |  | 849999.75 | 255402.15 | 233830.55 | 360767.05 |  | OK
849999.75
|  |  | CHECK | OK | OK | OK | OK

## LP_EIN
LP | Eindhoven |  |  | Country | NL |  | 22120 |  |  |  | 203858 | 2023 | [5 empty] | Budget 2023 | 72854 | 2024 | [5 empty] | Budget 2024 | 57328 | 2025 | [5 empty] | Budget 2025 | 73676 | OK
|  |  |  | Daily rate | 360 |  | ERDF |  |  | 65% | 132507.7 | [6 empty] | ERDF | 47355.1 | [6 empty] | ERDF | 37263.2 | [6 empty] | ERDF | 47889.4 | OK
[7 empty] | National Co-financing |  |  | 35% | 71350.3 | [6 empty] | Nat. Co-fin | 25498.9 | [6 empty] | Nat. Co-fin | 20064.8 | [6 empty] | Nat. Co-fin | 25786.6 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 21 | 7560 | 378 | 0 |  | 0 | 0 | 7938 | 9 | 3240 | 162 | 0 |  | 0 | 0 | 3402 | 6 | 2160 | 108 | 0 |  | 0 | 0 | 2268 | 6 | 2160 | 108 | 0 |  | 0 | 0 | 2268 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 360 | 18 |  |  |  | 0 | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 16 | 5760 | 288 |  |  |  |  | 6048 | 4 | 1440 | 72 |  |  |  |  | 1512 | 6 | 2160 | 108 |  |  |  |  | 2268 | 6 | 2160 | 108 |  |  |  |  | 2268 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 4 | 1440 | 72 | 0 |  | 0 | 0 | 1512 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 360 | 18 | 0 |  | 0 | 0 | 378 | 3 | 1080 | 54 | 0 |  | 0 | 0 | 1134 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 2 | 720 | 36 |  |  |  |  | 756 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 27 | 9720 | 486 | 0 |  | 38000 | 0 | 48206 | 9 | 3240 | 162 | 0 |  | 6000 | 0 | 9402 | 9 | 3240 | 162 | 0 |  | 16000 | 0 | 19402 | 9 | 3240 | 162 | 0 |  | 16000 | 0 | 19402 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 12 | 4320 | 216 |  | First Level Control | 10000 |  | 14536 | 4 | 1440 | 72 |  | First Level Control | 2000 |  | 3512 | 4 | 1440 | 72 |  | First Level Control | 4000 |  | 5512 | 4 | 1440 | 72 |  | First Level Control | 4000 |  | 5512 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 12 | 4320 | 216 |  | Ext. Project Coordination | 28000 |  | 32536 | 4 | 1440 | 72 |  | Ext. Project Coordination | 4000 |  | 5512 | 4 | 1440 | 72 |  | Ext. Project Coordination | 12000 |  | 13512 | 4 | 1440 | 72 |  | Ext. Project Coordination | 12000 |  | 13512 | OK
1.3.3 | Closure Report | LP | All PPs | 3 | 1080 | 54 |  |  |  |  | 1134 | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 52 | 18720 | 936 | 0 |  | 38000 | 0 | 57656 | 18 | 6480 | 324 | 0 |  | 6000 | 0 | 12804 | 16 | 5760 | 288 | 0 |  | 16000 | 0 | 22048 | 18 | 6480 | 324 | 0 |  | 16000 | 0 | 22804 | OK
WP2 | TRANSNATIONAL ACTIVITIES | [34 empty] | OK
2.1 | Transnational Activities |  |  | 104 | 37440 | 1872 | 18650 |  | 25550 | 0 | 83512 | 42 | 15120 | 756 | 7400 |  | 18300 | 0 | 41576 | 31 | 11160 | 558 | 4650 |  | 3450 | 0 | 19818 | 31 | 11160 | 558 | 6600 |  | 3800 | 0 | 22118 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 1440 | 72 |  |  |  |  | 1512 | 4 | 1440 | 72 |  |  |  |  | 1512 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 12 | 4320 | 216 | 3500 | Exp. & non-staff Travel | 7600 |  | 15636 | 12 | 4320 | 216 | 3500 | Exp. & non-staff Travel | 7600 |  | 15636 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 2880 | 144 | 0 | Ext. Meeting Organisation | 8000 |  | 11024 | 8 | 2880 | 144 | 0 | Ext. Meeting Organisation | 8000 |  | 11024 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 2160 | 108 | 2500 | Exp. & non-staff Travel | 1200 |  | 5968 | 6 | 2160 | 108 | 2500 | Exp. & non-staff Travel | 1200 |  | 5968 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 2160 | 108 | 2200 | Exp. & non-staff Travel | 1100 |  | 5568 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 2200 | Exp. & non-staff Travel | 1100 |  | 5568 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 2160 | 108 | 350 | Exp. & non-staff Travel | 350 |  | 2968 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 350 | Exp. & non-staff Travel | 350 |  | 2968 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 2160 | 108 | 1100 | Exp. & non-staff Travel | 1100 |  | 4468 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 1100 | Exp. & non-staff Travel | 1100 |  | 4468 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 2160 | 108 | 1000 | Exp. & non-staff Travel | 900 |  | 4168 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 1000 | Exp. & non-staff Travel | 900 |  | 4168 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 2160 | 108 | 2200 | Exp. & non-staff Travel | 1100 |  | 5568 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 2200 | Exp. & non-staff Travel | 1100 |  | 5568 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 2160 | 108 | 1200 | Exp. & non-staff Travel | 1100 |  | 4568 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 1200 | Exp. & non-staff Travel | 1100 |  | 4568 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 2160 | 108 | 2000 | Exp. & non-staff Travel | 1000 |  | 5268 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 2000 | Exp. & non-staff Travel | 1000 |  | 5268 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 2160 | 108 | 1200 | Exp. & non-staff Travel | 600 |  | 4068 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 2160 | 108 | 1200 | Exp. & non-staff Travel | 600 |  | 4068 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 2160 | 108 |  |  |  |  | 2268 | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 10 | 3600 | 180 |  |  |  |  | 3780 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1800 | 90 |  |  |  |  | 1890 | 5 | 1800 | 90 |  |  |  |  | 1890 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 10 | 3600 | 180 | 1400 | Exp. & non-staff Travel | 1500 |  | 6680 | 10 | 3600 | 180 | 1400 | Exp. & non-staff Travel | 1500 |  | 6680 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.2 | Transnational communication |  |  | 31 | 11160 | 558 | 0 |  | 10000 | 0 | 21718 | 11 | 3960 | 198 | 0 |  | 6000 | 0 | 10158 | 4 | 1440 | 72 | 0 |  | 2000 | 0 | 3512 | 16 | 5760 | 288 | 0 |  | 2000 | 0 | 8048 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 2 | 720 | 36 |  | Ext. Communication | 5000 |  | 5756 | 2 | 720 | 36 |  | Ext. Communication | 5000 |  | 5756 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 12 | 4320 | 216 |  |  |  |  | 4536 | 4 | 1440 | 72 |  |  |  |  | 1512 | 4 | 1440 | 72 |  |  |  |  | 1512 | 4 | 1440 | 72 |  |  |  |  | 1512 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 6 | 2160 | 108 |  | Ext. Communication | 5000 |  | 7268 |  | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication | 2000 |  | 2000 | 6 | 2160 | 108 |  | Ext. Communication | 2000 |  | 4268 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 2160 | 108 |  |  |  |  | 2268 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 2160 | 108 |  |  |  |  | 2268 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 135 | 48600 | 2430 | 18650 |  | 35550 | 0 | 105230 | 53 | 19080 | 954 | 7400 |  | 24300 | 0 | 51734 | 35 | 12600 | 630 | 4650 |  | 5450 | 0 | 23330 | 47 | 16920 | 846 | 6600 |  | 5800 | 0 | 30166 | OK
WP3 | LOCAL ACTIVITIES | [34 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 7920 | 396 | 0 |  | 4000 | 0 | 12316 | 14 | 5040 | 252 | 0 |  | 0 | 0 | 5292 | 4 | 1440 | 72 | 0 |  | 2000 | 0 | 3512 | 4 | 1440 | 72 | 0 |  | 2000 | 0 | 3512 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 1080 | 54 |  |  |  |  | 1134 | 3 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 360 | 18 |  | Ext. Meeting Organisation | 2400 |  | 2778 | 1 | 360 | 18 |  | Ext. Meeting Organisation |  |  | 378 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 2880 | 144 |  | Ext. Meeting Organisation | 1600 |  | 4624 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 1440 | 72 |  | Ext. Meeting Organisation | 800 |  | 2312 | 4 | 1440 | 72 |  | Ext. Meeting Organisation | 800 |  | 2312 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 720 | 36 |  |  |  |  | 756 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 1440 | 72 |  |  |  |  | 1512 | 4 | 1440 | 72 |  |  |  |  | 1512 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 1440 | 72 | 0 |  | 6000 | 2000 | 9512 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 1440 | 72 | 0 |  | 0 | 0 | 1512 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 | 2 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 720 | 36 |  | Ext. Project Coordination | 6000 | 2000 | 8756 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 720 | 36 |  | Ext. Project Coordination |  |  | 756 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 3600 | 180 | 0 |  | 0 | 0 | 3780 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 1800 | 90 | 0 |  | 0 | 0 | 1890 | 5 | 1800 | 90 | 0 |  | 0 | 0 | 1890 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 1800 | 90 |  |  |  |  | 1890 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1800 | 90 |  |  |  |  | 1890 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 1800 | 90 |  |  |  |  | 1890 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1800 | 90 |  |  |  |  | 1890 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 38 | 13680 | 684 | 0 |  | 1000 | 0 | 15364 | 8 | 2880 | 144 | 0 |  | 0 | 0 | 3024 | 12 | 4320 | 216 | 0 |  | 500 | 0 | 5036 | 18 | 6480 | 324 | 0 |  | 500 | 0 | 7304 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 360 | 18 |  |  |  |  | 378 | 1 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 30 | 10800 | 540 |  |  |  |  | 11340 | 6 | 2160 | 108 |  |  |  |  | 2268 | 12 | 4320 | 216 |  |  |  |  | 4536 | 12 | 4320 | 216 |  |  |  |  | 4536 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 3 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 1080 | 54 |  |  |  |  | 1134 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 1080 | 54 |  |  |  |  | 1134 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 74 | 26640 | 1332 | 0 |  | 11000 | 2000 | 40972 | 22 | 7920 | 396 | 0 |  | 0 | 0 | 8316 | 25 | 9000 | 450 | 0 |  | 2500 | 0 | 11950 | 27 | 9720 | 486 | 0 |  | 8500 | 2000 | 20706 | OK
|  |  |  | 261 | 93960 | 4698 | 18650 |  | 84550 | 2000 | 203858 | 173 | 33480 | 1674 | 7400 |  | 30300 | 0 | 72854 | 20760 | 27360 | 1368 | 4650 |  | 23950 | 0 | 57328 | 0 | 33120 | 1656 | 6600 |  | 30300 | 2000 | 73676 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 93960 | 33480 | 27360 | 33120 |  | OK
|  | Total |  | 93960 | 33480 | 27360 | 33120 |  | OK
| Office and Admin | Office and Administration |  | 4698 | 1674 | 1368 | 1656 |  | OK
|  | Total |  | 4698 | 1674 | 1368 | 1656 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 18650 | 7400 | 4650 | 6600 |  | OK
|  | Total |  | 18650 | 7400 | 4650 | 6600 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 34000 | 4000 | 12000 | 18000 |  | OK
|  | Ext. Meeting Organisation |  | 12000 | 8000 | 2000 | 2000 |  | OK
|  | Ext. Communication |  | 11000 | 6000 | 2500 | 2500 |  | OK
|  | Exp. & non-staff Travel |  | 17550 | 10300 | 3450 | 3800 |  | OK
|  | First Level Control |  | 10000 | 2000 | 4000 | 4000 |  | OK
|  | Total |  | 84550 | 30300 | 23950 | 30300 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 203858 | 72854 | 57328 | 73676 |  | OK
203858
|  |  | CHECK | OK | OK | OK | OK

## P2_AAR
P2 | Aarhus |  |  | Country | DK |  | Total Budget |  |  |  | 94478.5 | 2023 | [5 empty] | Budget 2023 | 32130.9 | 2024 | [5 empty] | Budget 2024 | 24551.3 | 2025 | [5 empty] | Budget 2025 | 37796.3 | OK
|  |  |  | Daily rate | 290 |  | ERDF |  |  | 65% | 61411.025 | [6 empty] | ERDF | 20885.085 | [6 empty] | ERDF | 15958.345 | [6 empty] | ERDF | 24567.595 | OK
[7 empty] | National Co-financing |  |  | 35% | 33067.475 | [6 empty] | Nat. Co-fin | 11245.815 | [6 empty] | Nat. Co-fin | 8592.955 | [6 empty] | Nat. Co-fin | 13228.705 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 2610 | 130.5 | 0 |  | 0 | 0 | 2740.5 | 5 | 1450 | 72.5 | 0 |  | 0 | 0 | 1522.5 | 2 | 580 | 29 | 0 |  | 0 | 0 | 609 | 2 | 580 | 29 | 0 |  | 0 | 0 | 609 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 290 | 14.5 |  |  |  | 0 | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 1450 | 72.5 |  |  |  |  | 1522.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 870 | 43.5 | 0 |  | 0 | 0 | 913.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 290 | 14.5 | 0 |  | 0 | 0 | 304.5 | 2 | 580 | 29 | 0 |  | 0 | 0 | 609 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 2610 | 130.5 | 0 |  | 3600 | 0 | 6340.5 | 2 | 580 | 29 | 0 |  | 1200 | 0 | 1809 | 3 | 870 | 43.5 | 0 |  | 1200 | 0 | 2113.5 | 4 | 1160 | 58 | 0 |  | 1200 | 0 | 2418 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1740 | 87 |  | First Level Control | 3600 |  | 5427 | 2 | 580 | 29 |  | First Level Control | 1200 |  | 1809 | 2 | 580 | 29 |  | First Level Control | 1200 |  | 1809 | 2 | 580 | 29 |  | First Level Control | 1200 |  | 1809 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 6090 | 304.5 | 0 |  | 3600 | 0 | 9994.5 | 7 | 2030 | 101.5 | 0 |  | 1200 | 0 | 3331.5 | 6 | 1740 | 87 | 0 |  | 1200 | 0 | 3027 | 8 | 2320 | 116 | 0 |  | 1200 | 0 | 3636 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 25230 | 1261.5 | 11250 |  | 13950 | 0 | 51691.5 | 29 | 8410 | 420.5 | 3800 |  | 8800 | 0 | 21430.5 | 29 | 8410 | 420.5 | 3150 |  | 2050 | 0 | 14030.5 | 29 | 8410 | 420.5 | 4300 |  | 3100 | 0 | 16230.5 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 1160 | 58 |  |  |  |  | 1218 | 4 | 1160 | 58 | 0 |  |  |  | 1218 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 870 | 43.5 |  |  |  |  | 913.5 | 3 | 870 | 43.5 | 0 |  |  |  | 913.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 2320 | 116 | 1600 | Exp. & non-staff Travel | 800 |  | 4836 | 8 | 2320 | 116 | 1600 | Exp. & non-staff Travel | 800 |  | 4836 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 1740 | 87 | 0 | Ext. Meeting Organisation | 8000 |  | 9827 | 6 | 1740 | 87 | 0 | Ext. Meeting Organisation | 8000 |  | 9827 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 1740 | 87 | 1700 | Exp. & non-staff Travel | 900 |  | 4427 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 1700 | Exp. & non-staff Travel | 900 |  | 4427 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 1740 | 87 | 800 | Exp. & non-staff Travel | 500 |  | 3127 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 800 | Exp. & non-staff Travel | 500 |  | 3127 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 1740 | 87 | 0 |  |  |  | 1827 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1740 | 87 | 0 |  | 0 |  | 1827 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 1740 | 87 | 650 | Exp. & non-staff Travel | 650 |  | 3127 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 650 | Exp. & non-staff Travel | 650 |  | 3127 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 1740 | 87 | 1000 | Exp. & non-staff Travel | 1000 |  | 3827 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 1000 | Exp. & non-staff Travel | 1000 |  | 3827 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 1740 | 87 | 1000 | Exp. & non-staff Travel | 500 |  | 3327 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 1000 | Exp. & non-staff Travel | 500 |  | 3327 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 1740 | 87 | 1600 | Exp. & non-staff Travel | 900 |  | 4327 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 1600 | Exp. & non-staff Travel | 900 |  | 4327 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 1740 | 87 | 700 | Exp. & non-staff Travel | 700 |  | 3227 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1740 | 87 | 700 | Exp. & non-staff Travel | 700 |  | 3227 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 1740 | 87 |  |  |  |  | 1827 | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 1740 | 87 |  |  |  |  | 1827 |  | 0 | 0 |  |  |  |  | 0 | 3 | 870 | 43.5 |  |  |  |  | 913.5 | 3 | 870 | 43.5 |  |  |  |  | 913.5 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 1740 | 87 | 2200 |  |  |  | 4027 | 6 | 1740 | 87 | 2200 |  |  |  | 4027 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 4930 | 246.5 | 0 |  | 0 | 0 | 5176.5 | 7 | 2030 | 101.5 | 0 |  | 0 | 0 | 2131.5 | 1 | 290 | 14.5 | 0 |  | 0 | 0 | 304.5 | 9 | 2610 | 130.5 | 0 |  | 0 | 0 | 2740.5 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 870 | 43.5 |  |  |  |  | 913.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 870 | 43.5 |  |  |  |  | 913.5 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1740 | 87 |  |  |  |  | 1827 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1740 | 87 |  |  |  |  | 1827 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 30160 | 1508 | 11250 |  | 13950 | 0 | 56868 | 36 | 10440 | 522 | 3800 |  | 8800 | 0 | 23562 | 30 | 8700 | 435 | 3150 |  | 2050 | 0 | 14335 | 38 | 11020 | 551 | 4300 |  | 3100 | 0 | 18971 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 6380 | 319 | 0 |  | 4000 | 0 | 10699 | 14 | 4060 | 203 | 0 |  | 0 | 0 | 4263 | 4 | 1160 | 58 | 0 |  | 2000 | 0 | 3218 | 4 | 1160 | 58 | 0 |  | 2000 | 0 | 3218 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 870 | 43.5 |  |  |  |  | 913.5 | 3 | 870 | 43.5 |  |  |  |  | 913.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 290 | 14.5 |  | Ext. Meeting Organisation | 2400 |  | 2704.5 | 1 | 290 | 14.5 |  | Ext. Meeting Organisation |  |  | 304.5 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 2320 | 116 |  | Ext. Meeting Organisation | 1600 |  | 4036 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 1160 | 58 |  | Ext. Meeting Organisation | 800 |  | 2018 | 4 | 1160 | 58 |  | Ext. Meeting Organisation | 800 |  | 2018 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 580 | 29 |  |  |  |  | 609 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 1160 | 58 |  |  |  |  | 1218 | 4 | 1160 | 58 |  |  |  |  | 1218 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 1160 | 58 | 0 |  | 6000 | 2000 | 9218 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 1160 | 58 | 0 |  | 0 | 0 | 1218 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 | 2 | 580 | 29 |  |  |  |  | 609 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 580 | 29 |  | Ext. Project Coordination | 6000 | 2000 | 8609 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 580 | 29 |  | Ext. Project Coordination |  |  | 609 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 2900 | 145 | 0 |  | 0 | 0 | 3045 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 1450 | 72.5 | 0 |  | 0 | 0 | 1522.5 | 5 | 1450 | 72.5 | 0 |  | 0 | 0 | 1522.5 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 1450 | 72.5 |  |  |  |  | 1522.5 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1450 | 72.5 |  |  |  |  | 1522.5 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 1450 | 72.5 |  |  |  |  | 1522.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1450 | 72.5 |  |  |  |  | 1522.5 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 3480 | 174 | 0 |  | 1000 | 0 | 4654 | 3.2 | 928 | 46.4 | 0 |  | 0 | 0 | 974.4 | 2.4 | 696 | 34.8 | 0 |  | 500 | 0 | 1230.8 | 6.4 | 1856 | 92.8 | 0 |  | 500 | 0 | 2448.8 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 290 | 14.5 |  |  |  |  | 304.5 | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1740 | 87 |  |  |  |  | 1827 | 1.2 | 348 | 17.4 |  |  |  |  | 365.4 | 2.4 | 696 | 34.8 |  |  |  |  | 730.8 | 2.4 | 696 | 34.8 |  |  |  |  | 730.8 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 290 | 14.5 |  |  |  |  | 304.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 290 | 14.5 |  |  |  |  | 304.5 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 870 | 43.5 |  |  |  |  | 913.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 870 | 43.5 |  |  |  |  | 913.5 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 13920 | 696 | 0 |  | 11000 | 2000 | 27616 | 17.2 | 4988 | 249.4 | 0 |  | 0 | 0 | 5237.4 | 15.4 | 4466 | 223.3 | 0 |  | 2500 | 0 | 7189.3 | 15.4 | 4466 | 223.3 | 0 |  | 8500 | 2000 | 15189.3 | OK
|  |  |  | 173 | 50170 | 2508.5 | 11250 |  | 28550 | 2000 | 94478.5 | 173 | 17458 | 872.9 | 3800 |  | 10000 | 0 | 32130.9 | 20760 | 14906 | 745.3 | 3150 |  | 5750 | 0 | 24551.3 | 0 | 17806 | 890.3 | 4300 |  | 12800 | 2000 | 37796.3 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 50170 | 17458 | 14906 | 17806 |  | OK
|  | Total |  | 50170 | 17458 | 14906 | 17806 |  | OK
| Office and Admin | Office and Administration |  | 2508.5 | 872.9 | 745.3 | 890.3 |  | OK
|  | Total |  | 2508.5 | 872.9 | 745.3 | 890.3 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11250 | 3800 | 3150 | 4300 |  | OK
|  | Total |  | 11250 | 3800 | 3150 | 4300 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 12000 | 8000 | 2000 | 2000 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 5950 | 800 | 2050 | 3100 |  | OK
|  | First Level Control |  | 3600 | 1200 | 1200 | 1200 |  | OK
|  | Total |  | 28550 | 10000 | 5750 | 12800 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 94478.5 | 32130.9 | 24551.3 | 37796.3 |  | OK
94478.5
|  |  | CHECK | OK | OK | OK | OK

## P3_CAR
P3 | Cartagena |  |  | Country | ES |  | Total Budget |  |  |  | 74197 | 2023 | [5 empty] | Budget 2023 | 20477.8 | 2024 | [5 empty] | Budget 2024 | 22614.6 | 2025 | [5 empty] | Budget 2025 | 31104.6 | OK
|  |  |  | Daily rate | 180 |  | ERDF |  |  | 70% | 51937.9 | [6 empty] | ERDF | 14334.46 | [6 empty] | ERDF | 15830.22 | [6 empty] | ERDF | 21773.22 | OK
[7 empty] | National Co-financing |  |  | 30% | 22259.1 | [6 empty] | Nat. Co-fin | 6143.34 | [6 empty] | Nat. Co-fin | 6784.38 | [6 empty] | Nat. Co-fin | 9331.38 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 180 | 9 |  |  |  | 0 | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 900 | 45 |  |  |  |  | 945 | 1 | 180 | 9 |  |  |  |  | 189 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1620 | 81 | 0 |  | 3000 | 0 | 4701 | 2 | 360 | 18 | 0 |  | 1000 | 0 | 1378 | 3 | 540 | 27 | 0 |  | 1000 | 0 | 1567 | 4 | 720 | 36 | 0 |  | 1000 | 0 | 1756 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1080 | 54 |  | First Level Control | 3000 |  | 4134 | 2 | 360 | 18 |  | First Level Control | 1000 |  | 1378 | 2 | 360 | 18 |  | First Level Control | 1000 |  | 1378 | 2 | 360 | 18 |  | First Level Control | 1000 |  | 1378 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 3780 | 189 | 0 |  | 3000 | 0 | 6969 | 7 | 1260 | 63 | 0 |  | 1000 | 0 | 2323 | 6 | 1080 | 54 | 0 |  | 1000 | 0 | 2134 | 8 | 1440 | 72 | 0 |  | 1000 | 0 | 2512 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 15660 | 783 | 12300 |  | 13200 | 0 | 41943 | 29 | 5220 | 261 | 6200 |  | 1900 | 0 | 13581 | 29 | 5220 | 261 | 1700 |  | 7700 | 0 | 14881 | 29 | 5220 | 261 | 4400 |  | 3600 | 0 | 13481 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 | 0 |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 | 0 |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 1440 | 72 | 1800 | Exp. & non-staff Travel | 900 |  | 4212 | 8 | 1440 | 72 | 1800 | Exp. & non-staff Travel | 900 |  | 4212 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 1080 | 54 | 2200 | Exp. & non-staff Travel | 1000 |  | 4334 | 6 | 1080 | 54 | 2200 | Exp. & non-staff Travel | 1000 |  | 4334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 1080 | 54 | 800 | Exp. & non-staff Travel | 800 |  | 2734 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 800 | Exp. & non-staff Travel | 800 |  | 2734 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 1080 | 54 | 900 | Exp. & non-staff Travel | 900 |  | 2934 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 900 | Exp. & non-staff Travel | 900 |  | 2934 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 1080 | 54 | 0 |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 | 0 |  | 0 |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 1080 | 54 | 1450 | Exp. & non-staff Travel | 1450 |  | 4034 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1450 | Exp. & non-staff Travel | 1450 |  | 4034 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 1080 | 54 | 1500 | Exp. & non-staff Travel | 700 |  | 3334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1500 | Exp. & non-staff Travel | 700 |  | 3334 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 1080 | 54 | 700 | Exp. & non-staff Travel | 700 |  | 2534 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 700 | Exp. & non-staff Travel | 700 |  | 2534 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 1080 | 54 | 2200 |  |  |  | 3334 | 6 | 1080 | 54 | 2200 |  |  |  | 3334 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 3060 | 153 | 0 |  | 0 | 0 | 3213 | 7 | 1260 | 63 | 0 |  | 0 | 0 | 1323 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 |  |  |  |  | 1134 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 18720 | 936 | 12300 |  | 13200 | 0 | 45156 | 36 | 6480 | 324 | 6200 |  | 1900 | 0 | 14904 | 30 | 5400 | 270 | 1700 |  | 7700 | 0 | 15070 | 38 | 6840 | 342 | 4400 |  | 3600 | 0 | 15182 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 3960 | 198 | 0 |  | 4000 | 0 | 8158 | 14 | 2520 | 126 | 0 |  | 0 | 0 | 2646 | 4 | 720 | 36 | 0 |  | 2000 | 0 | 2756 | 4 | 720 | 36 | 0 |  | 2000 | 0 | 2756 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Meeting Organisation | 2100 |  | 2289 | 1 | 180 | 9 |  | Ext. Meeting Organisation |  |  | 189 |  | 0 | 0 |  | Ext. Meeting Organisation | 1050 |  | 1050 |  | 0 | 0 |  | Ext. Meeting Organisation | 1050 |  | 1050 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 1440 | 72 |  | Ext. Meeting Organisation | 1900 |  | 3412 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 950 |  | 1706 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 950 |  | 1706 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 720 | 36 | 0 |  | 6000 | 2000 | 8756 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 720 | 36 | 0 |  | 0 | 0 | 756 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  | Ext. Project Coordination | 6000 | 2000 | 8378 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 360 | 18 |  | Ext. Project Coordination |  |  | 378 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 1800 | 90 | 0 |  | 0 | 0 | 1890 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 2160 | 108 | 0 |  | 1000 | 0 | 3268 | 3.2 | 576 | 28.8 | 0 |  | 0 | 0 | 604.8 | 2.4 | 432 | 21.6 | 0 |  | 500 | 0 | 953.6 | 6.4 | 1152 | 57.6 | 0 |  | 500 | 0 | 1709.6 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1080 | 54 |  |  |  |  | 1134 | 1.2 | 216 | 10.8 |  |  |  |  | 226.8 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 8640 | 432 | 0 |  | 11000 | 2000 | 22072 | 17.2 | 3096 | 154.8 | 0 |  | 0 | 0 | 3250.8 | 15.4 | 2772 | 138.6 | 0 |  | 2500 | 0 | 5410.6 | 15.4 | 2772 | 138.6 | 0 |  | 8500 | 2000 | 13410.6 | OK
|  |  |  | 173 | 31140 | 1557 | 12300 |  | 27200 | 2000 | 74197 | 173 | 10836 | 541.8 | 6200 |  | 2900 | 0 | 20477.8 | 20760 | 9252 | 462.6 | 1700 |  | 11200 | 0 | 22614.6 | 0 | 11052 | 552.6 | 4400 |  | 13100 | 2000 | 31104.6 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 31140 | 10836 | 9252 | 11052 |  | OK
|  | Total |  | 31140 | 10836 | 9252 | 11052 |  | OK
| Office and Admin | Office and Administration |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
|  | Total |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 12300 | 6200 | 1700 | 4400 |  | OK
|  | Total |  | 12300 | 6200 | 1700 | 4400 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 10000 | 0 | 8000 | 2000 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 7200 | 1900 | 1700 | 3600 |  | OK
|  | First Level Control |  | 3000 | 1000 | 1000 | 1000 |  | OK
|  | Total |  | 27200 | 2900 | 11200 | 13100 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 74197 | 20477.8 | 22614.6 | 31104.6 |  | OK
74197
|  |  | CHECK | OK | OK | OK | OK

## P4_GDA
P4 | Gdańsk |  |  | Country | PL |  | Total Budget |  |  |  | 63347.5 | 2023 | [5 empty] | Budget 2023 | 16981.5 | 2024 | [5 empty] | Budget 2024 | 20695.5 | 2025 | [5 empty] | Budget 2025 | 25670.5 | OK
|  |  |  | Daily rate | 150 |  | ERDF |  |  | 80% | 50678 | [6 empty] | ERDF | 13585.2 | [6 empty] | ERDF | 16556.4 | [6 empty] | ERDF | 20536.4 | OK
[7 empty] | National Co-financing |  |  | 20% | 12669.5 | [6 empty] | Nat. Co-fin | 3396.3 | [6 empty] | Nat. Co-fin | 4139.1 | [6 empty] | Nat. Co-fin | 5134.1 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1350 | 67.5 | 0 |  | 0 | 0 | 1417.5 | 5 | 750 | 37.5 | 0 |  | 0 | 0 | 787.5 | 2 | 300 | 15 | 0 |  | 0 | 0 | 315 | 2 | 300 | 15 | 0 |  | 0 | 0 | 315 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 150 | 7.5 |  |  |  | 0 | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 750 | 37.5 |  |  |  |  | 787.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 450 | 22.5 | 0 |  | 0 | 0 | 472.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 150 | 7.5 | 0 |  | 0 | 0 | 157.5 | 2 | 300 | 15 | 0 |  | 0 | 0 | 315 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1350 | 67.5 | 0 |  | 0 | 0 | 1417.5 | 2 | 300 | 15 | 0 |  | 0 | 0 | 315 | 3 | 450 | 22.5 | 0 |  | 0 | 0 | 472.5 | 4 | 600 | 30 | 0 |  | 0 | 0 | 630 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 900 | 45 |  |  |  |  | 945 | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 3150 | 157.5 | 0 |  | 0 | 0 | 3307.5 | 7 | 1050 | 52.5 | 0 |  | 0 | 0 | 1102.5 | 6 | 900 | 45 | 0 |  | 0 | 0 | 945 | 8 | 1200 | 60 | 0 |  | 0 | 0 | 1260 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 13050 | 652.5 | 11150 |  | 12350 | 0 | 37202.5 | 29 | 4350 | 217.5 | 5700 |  | 1800 | 0 | 12067.5 | 29 | 4350 | 217.5 | 2150 |  | 8150 | 0 | 14867.5 | 29 | 4350 | 217.5 | 3300 |  | 2400 | 0 | 10267.5 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 600 | 30 |  |  |  |  | 630 | 4 | 600 | 30 | 0 |  |  |  | 630 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 450 | 22.5 |  |  |  |  | 472.5 | 3 | 450 | 22.5 | 0 |  |  |  | 472.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 1200 | 60 | 1600 | Exp. & non-staff Travel | 900 |  | 3760 | 8 | 1200 | 60 | 1600 | Exp. & non-staff Travel | 900 |  | 3760 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 900 | 45 | 1900 | Exp. & non-staff Travel | 900 |  | 3745 | 6 | 900 | 45 | 1900 | Exp. & non-staff Travel | 900 |  | 3745 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 900 | 45 | 850 | Exp. & non-staff Travel | 850 |  | 2645 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 850 | Exp. & non-staff Travel | 850 |  | 2645 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 900 | 45 | 0 | Ext. Meeting Organisation | 6000 |  | 6945 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 900 | 45 | 0 | Ext. Meeting Organisation | 6000 |  | 6945 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 900 | 45 | 650 | Exp. & non-staff Travel | 650 |  | 2245 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 650 | Exp. & non-staff Travel | 650 |  | 2245 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 900 | 45 | 650 | Exp. & non-staff Travel | 650 |  | 2245 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 650 | Exp. & non-staff Travel | 650 |  | 2245 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 900 | 45 | 1000 | Exp. & non-staff Travel | 1000 |  | 2945 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 1000 | Exp. & non-staff Travel | 1000 |  | 2945 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 900 | 45 | 0 |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 900 | 45 | 0 |  | 0 |  | 945 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 900 | 45 | 1700 | Exp. & non-staff Travel | 800 |  | 3445 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 1700 | Exp. & non-staff Travel | 800 |  | 3445 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 900 | 45 | 600 | Exp. & non-staff Travel | 600 |  | 2145 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 900 | 45 | 600 | Exp. & non-staff Travel | 600 |  | 2145 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 900 | 45 |  |  |  |  | 945 | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | 3 | 450 | 22.5 |  |  |  |  | 472.5 | 3 | 450 | 22.5 |  |  |  |  | 472.5 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 900 | 45 | 2200 |  |  |  | 3145 | 6 | 900 | 45 | 2200 |  |  |  | 3145 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 2550 | 127.5 | 0 |  | 0 | 0 | 2677.5 | 7 | 1050 | 52.5 | 0 |  | 0 | 0 | 1102.5 | 1 | 150 | 7.5 | 0 |  | 0 | 0 | 157.5 | 9 | 1350 | 67.5 | 0 |  | 0 | 0 | 1417.5 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 450 | 22.5 |  |  |  |  | 472.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 450 | 22.5 |  |  |  |  | 472.5 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 900 | 45 |  |  |  |  | 945 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 15600 | 780 | 11150 |  | 12350 | 0 | 39880 | 36 | 5400 | 270 | 5700 |  | 1800 | 0 | 13170 | 30 | 4500 | 225 | 2150 |  | 8150 | 0 | 15025 | 38 | 5700 | 285 | 3300 |  | 2400 | 0 | 11685 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 3300 | 165 | 0 |  | 3600 | 0 | 7065 | 14 | 2100 | 105 | 0 |  | 0 | 0 | 2205 | 4 | 600 | 30 | 0 |  | 1800 | 0 | 2430 | 4 | 600 | 30 | 0 |  | 1800 | 0 | 2430 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 450 | 22.5 |  |  |  |  | 472.5 | 3 | 450 | 22.5 |  |  |  |  | 472.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 150 | 7.5 |  | Ext. Meeting Organisation | 2400 |  | 2557.5 | 1 | 150 | 7.5 |  | Ext. Meeting Organisation |  |  | 157.5 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 1200 | 60 |  | Ext. Meeting Organisation | 1200 |  | 2460 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 600 | 30 |  | Ext. Meeting Organisation | 600 |  | 1230 | 4 | 600 | 30 |  | Ext. Meeting Organisation | 600 |  | 1230 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 300 | 15 |  |  |  |  | 315 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 600 | 30 |  |  |  |  | 630 | 4 | 600 | 30 |  |  |  |  | 630 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 600 | 30 | 0 |  | 6000 | 2000 | 8630 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 600 | 30 | 0 |  | 0 | 0 | 630 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 | 2 | 300 | 15 |  |  |  |  | 315 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 300 | 15 |  | Ext. Project Coordination | 6000 | 2000 | 8315 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 300 | 15 |  | Ext. Project Coordination |  |  | 315 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 1500 | 75 | 0 |  | 0 | 0 | 1575 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 750 | 37.5 | 0 |  | 0 | 0 | 787.5 | 5 | 750 | 37.5 | 0 |  | 0 | 0 | 787.5 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 | 5 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 750 | 37.5 |  |  |  |  | 787.5 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 1800 | 90 | 0 |  | 1000 | 0 | 2890 | 3.2 | 480 | 24 | 0 |  | 0 | 0 | 504 | 2.4 | 360 | 18 | 0 |  | 500 | 0 | 878 | 6.4 | 960 | 48 | 0 |  | 500 | 0 | 1508 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 150 | 7.5 |  |  |  |  | 157.5 | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 900 | 45 |  |  |  |  | 945 | 1.2 | 180 | 9 |  |  |  |  | 189 | 2.4 | 360 | 18 |  |  |  |  | 378 | 2.4 | 360 | 18 |  |  |  |  | 378 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 150 | 7.5 |  |  |  |  | 157.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 150 | 7.5 |  |  |  |  | 157.5 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 450 | 22.5 |  |  |  |  | 472.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 450 | 22.5 |  |  |  |  | 472.5 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 7200 | 360 | 0 |  | 10600 | 2000 | 20160 | 17.2 | 2580 | 129 | 0 |  | 0 | 0 | 2709 | 15.4 | 2310 | 115.5 | 0 |  | 2300 | 0 | 4725.5 | 15.4 | 2310 | 115.5 | 0 |  | 8300 | 2000 | 12725.5 | OK
|  |  |  | 173 | 25950 | 1297.5 | 11150 |  | 22950 | 2000 | 63347.5 | 173 | 9030 | 451.5 | 5700 |  | 1800 | 0 | 16981.5 | 20760 | 7710 | 385.5 | 2150 |  | 10450 | 0 | 20695.5 | 0 | 9210 | 460.5 | 3300 |  | 10700 | 2000 | 25670.5 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 25950 | 9030 | 7710 | 9210 |  | OK
|  | Total |  | 25950 | 9030 | 7710 | 9210 |  | OK
| Office and Admin | Office and Administration |  | 1297.5 | 451.5 | 385.5 | 460.5 |  | OK
|  | Total |  | 1297.5 | 451.5 | 385.5 | 460.5 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11150 | 5700 | 2150 | 3300 |  | OK
|  | Total |  | 11150 | 5700 | 2150 | 3300 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 9600 | 0 | 7800 | 1800 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 6350 | 1800 | 2150 | 2400 |  | OK
|  | First Level Control |  | 0 | 0 | 0 | 0 |  | OK
|  | Total |  | 22950 | 1800 | 10450 | 10700 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 63347.5 | 16981.5 | 20695.5 | 25670.5 |  | OK
63347.5
|  |  | CHECK | OK | OK | OK | OK

## P5_IAS
P5 | Iași |  |  | Country | RO |  | Total Budget |  |  |  | 68697 | 2023 | [5 empty] | Budget 2023 | 19277.8 | 2024 | [5 empty] | Budget 2024 | 20614.6 | 2025 | [5 empty] | Budget 2025 | 28804.6 | OK
|  |  |  | Daily rate | 180 |  | ERDF |  |  | 80% | 54957.6 | [6 empty] | ERDF | 15422.24 | [6 empty] | ERDF | 16491.68 | [6 empty] | ERDF | 23043.68 | OK
[7 empty] | National Co-financing |  |  | 20% | 13739.4 | [6 empty] | Nat. Co-fin | 3855.56 | [6 empty] | Nat. Co-fin | 4122.92 | [6 empty] | Nat. Co-fin | 5760.92 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 180 | 9 |  |  |  | 0 | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 900 | 45 |  |  |  |  | 945 | 1 | 180 | 9 |  |  |  |  | 189 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 4 | 720 | 36 | 0 |  | 0 | 0 | 756 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1080 | 54 |  |  |  |  | 1134 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 3780 | 189 | 0 |  | 0 | 0 | 3969 | 7 | 1260 | 63 | 0 |  | 0 | 0 | 1323 | 6 | 1080 | 54 | 0 |  | 0 | 0 | 1134 | 8 | 1440 | 72 | 0 |  | 0 | 0 | 1512 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 15660 | 783 | 11850 |  | 12750 | 0 | 41043 | 29 | 5220 | 261 | 6000 |  | 1900 | 0 | 13381 | 29 | 5220 | 261 | 1600 |  | 7600 | 0 | 14681 | 29 | 5220 | 261 | 4250 |  | 3250 | 0 | 12981 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 | 0 |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 | 0 |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 1440 | 72 | 1800 | Exp. & non-staff Travel | 900 |  | 4212 | 8 | 1440 | 72 | 1800 | Exp. & non-staff Travel | 900 |  | 4212 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 1080 | 54 | 1900 | Exp. & non-staff Travel | 1000 |  | 4034 | 6 | 1080 | 54 | 1900 | Exp. & non-staff Travel | 1000 |  | 4034 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 1080 | 54 | 950 | Exp. & non-staff Travel | 950 |  | 3034 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 950 | Exp. & non-staff Travel | 950 |  | 3034 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 1080 | 54 | 0 |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 | 0 |  | 0 |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 1080 | 54 | 650 | Exp. & non-staff Travel | 650 |  | 2434 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 650 | Exp. & non-staff Travel | 650 |  | 2434 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 1080 | 54 | 1100 | Exp. & non-staff Travel | 1100 |  | 3334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1100 | Exp. & non-staff Travel | 1100 |  | 3334 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 1080 | 54 | 1800 | Exp. & non-staff Travel | 800 |  | 3734 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1800 | Exp. & non-staff Travel | 800 |  | 3734 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 600 |  | 2334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 600 |  | 2334 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 1080 | 54 | 2300 |  |  |  | 3434 | 6 | 1080 | 54 | 2300 |  |  |  | 3434 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 3060 | 153 | 0 |  | 0 | 0 | 3213 | 7 | 1260 | 63 | 0 |  | 0 | 0 | 1323 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 |  |  |  |  | 1134 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 18720 | 936 | 11850 |  | 12750 | 0 | 44256 | 36 | 6480 | 324 | 6000 |  | 1900 | 0 | 14704 | 30 | 5400 | 270 | 1600 |  | 7600 | 0 | 14870 | 38 | 6840 | 342 | 4250 |  | 3250 | 0 | 14682 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 3960 | 198 | 0 |  | 2400 | 0 | 6558 | 14 | 2520 | 126 | 0 |  | 0 | 0 | 2646 | 4 | 720 | 36 | 0 |  | 1200 | 0 | 1956 | 4 | 720 | 36 | 0 |  | 1200 | 0 | 1956 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Meeting Organisation | 1200 |  | 1389 | 1 | 180 | 9 |  | Ext. Meeting Organisation |  |  | 189 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 1440 | 72 |  | Ext. Meeting Organisation | 1200 |  | 2712 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 600 |  | 1356 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 600 |  | 1356 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 720 | 36 | 0 |  | 6000 | 2000 | 8756 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 720 | 36 | 0 |  | 0 | 0 | 756 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  | Ext. Project Coordination | 6000 | 2000 | 8378 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 360 | 18 |  | Ext. Project Coordination |  |  | 378 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 1800 | 90 | 0 |  | 0 | 0 | 1890 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 2160 | 108 | 0 |  | 1000 | 0 | 3268 | 3.2 | 576 | 28.8 | 0 |  | 0 | 0 | 604.8 | 2.4 | 432 | 21.6 | 0 |  | 500 | 0 | 953.6 | 6.4 | 1152 | 57.6 | 0 |  | 500 | 0 | 1709.6 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1080 | 54 |  |  |  |  | 1134 | 1.2 | 216 | 10.8 |  |  |  |  | 226.8 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 8640 | 432 | 0 |  | 9400 | 2000 | 20472 | 17.2 | 3096 | 154.8 | 0 |  | 0 | 0 | 3250.8 | 15.4 | 2772 | 138.6 | 0 |  | 1700 | 0 | 4610.6 | 15.4 | 2772 | 138.6 | 0 |  | 7700 | 2000 | 12610.6 | OK
|  |  |  | 173 | 31140 | 1557 | 11850 |  | 22150 | 2000 | 68697 | 173 | 10836 | 541.8 | 6000 |  | 1900 | 0 | 19277.8 | 20760 | 9252 | 462.6 | 1600 |  | 9300 | 0 | 20614.6 | 0 | 11052 | 552.6 | 4250 |  | 10950 | 2000 | 28804.6 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 31140 | 10836 | 9252 | 11052 |  | OK
|  | Total |  | 31140 | 10836 | 9252 | 11052 |  | OK
| Office and Admin | Office and Administration |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
|  | Total |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11850 | 6000 | 1600 | 4250 |  | OK
|  | Total |  | 11850 | 6000 | 1600 | 4250 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 8400 | 0 | 7200 | 1200 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 6750 | 1900 | 1600 | 3250 |  | OK
|  | First Level Control |  | 0 | 0 | 0 | 0 |  | OK
|  | Total |  | 22150 | 1900 | 9300 | 10950 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 68697 | 19277.8 | 20614.6 | 28804.6 |  | OK
68697
|  |  | CHECK | OK | OK | OK | OK

## P6_VES
P6 | Veszprém |  |  | Country | HU |  | Total Budget |  |  |  | 62289 | 2023 | [5 empty] | Budget 2023 | 16085.2 | 2024 | [5 empty] | Budget 2024 | 19376.4 | 2025 | [5 empty] | Budget 2025 | 26827.4 | OK
|  |  |  | Daily rate | 120 |  | ERDF |  |  | 80% | 49831.2 | [6 empty] | ERDF | 12868.16 | [6 empty] | ERDF | 15501.12 | [6 empty] | ERDF | 21461.92 | OK
[7 empty] | National Co-financing |  |  | 20% | 12457.8 | [6 empty] | Nat. Co-fin | 3217.04 | [6 empty] | Nat. Co-fin | 3875.28 | [6 empty] | Nat. Co-fin | 5365.48 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1080 | 54 | 0 |  | 0 | 0 | 1134 | 5 | 600 | 30 | 0 |  | 0 | 0 | 630 | 2 | 240 | 12 | 0 |  | 0 | 0 | 252 | 2 | 240 | 12 | 0 |  | 0 | 0 | 252 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 120 | 6 |  |  |  | 0 | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 600 | 30 |  |  |  |  | 630 | 1 | 120 | 6 |  |  |  |  | 126 | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 360 | 18 | 0 |  | 0 | 0 | 378 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 120 | 6 | 0 |  | 0 | 0 | 126 | 2 | 240 | 12 | 0 |  | 0 | 0 | 252 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1080 | 54 | 0 |  | 5000 | 0 | 6134 | 2 | 240 | 12 | 0 |  | 1000 | 0 | 1252 | 3 | 360 | 18 | 0 |  | 2000 | 0 | 2378 | 4 | 480 | 24 | 0 |  | 2000 | 0 | 2504 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 720 | 36 |  | Ext. Project Coordination | 5000 |  | 5756 | 2 | 240 | 12 |  | Ext. Project Coordination | 1000 |  | 1252 | 2 | 240 | 12 |  | Ext. Project Coordination | 2000 |  | 2252 | 2 | 240 | 12 |  | Ext. Project Coordination | 2000 |  | 2252 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 2520 | 126 | 0 |  | 5000 | 0 | 7646 | 7 | 840 | 42 | 0 |  | 1000 | 0 | 1882 | 6 | 720 | 36 | 0 |  | 2000 | 0 | 2756 | 8 | 960 | 48 | 0 |  | 2000 | 0 | 3008 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 10440 | 522 | 11551 |  | 12540 | 0 | 35053 | 29 | 3480 | 174 | 5700 |  | 1800 | 0 | 11154 | 29 | 3480 | 174 | 1650 |  | 7550 | 0 | 12854 | 29 | 3480 | 174 | 4201 |  | 3190 | 0 | 11045 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 480 | 24 |  |  |  |  | 504 | 4 | 480 | 24 | 0 |  |  |  | 504 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 360 | 18 |  |  |  |  | 378 | 3 | 360 | 18 | 0 |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 960 | 48 | 1700 | Exp. & non-staff Travel | 800 |  | 3508 | 8 | 960 | 48 | 1700 | Exp. & non-staff Travel | 800 |  | 3508 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 720 | 36 | 1800 | Exp. & non-staff Travel | 1000 |  | 3556 | 6 | 720 | 36 | 1800 | Exp. & non-staff Travel | 1000 |  | 3556 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 720 | 36 | 1000 | Exp. & non-staff Travel | 900 |  | 2656 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 1000 | Exp. & non-staff Travel | 900 |  | 2656 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 720 | 36 | 650 | Exp. & non-staff Travel | 650 |  | 2056 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 650 | Exp. & non-staff Travel | 650 |  | 2056 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 720 | 36 | 0 |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 | 6 | 720 | 36 | 0 |  | 0 |  | 756 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 720 | 36 | 0 | Ext. Meeting Organisation | 6000 |  | 6756 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 720 | 36 | 0 | Ext. Meeting Organisation | 6000 |  | 6756 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 720 | 36 | 1000 | Exp. & non-staff Travel | 1000 |  | 2756 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 1000 | Exp. & non-staff Travel | 1000 |  | 2756 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 720 | 36 | 750 | Exp. & non-staff Travel | 750 |  | 2256 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 750 | Exp. & non-staff Travel | 750 |  | 2256 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 720 | 36 | 1800 | Exp. & non-staff Travel | 800 |  | 3356 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 1800 | Exp. & non-staff Travel | 800 |  | 3356 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 720 | 36 | 651 | Exp. & non-staff Travel | 640 |  | 2047 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 720 | 36 | 651 | Exp. & non-staff Travel | 640 |  | 2047 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 720 | 36 |  |  |  |  | 756 | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 | 3 | 360 | 18 |  |  |  |  | 378 | 3 | 360 | 18 |  |  |  |  | 378 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 720 | 36 | 2200 |  |  |  | 2956 | 6 | 720 | 36 | 2200 |  |  |  | 2956 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 2040 | 102 | 0 |  | 0 | 0 | 2142 | 7 | 840 | 42 | 0 |  | 0 | 0 | 882 | 1 | 120 | 6 | 0 |  | 0 | 0 | 126 | 9 | 1080 | 54 | 0 |  | 0 | 0 | 1134 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 360 | 18 |  |  |  |  | 378 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 720 | 36 |  |  |  |  | 756 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 12480 | 624 | 11551 |  | 12540 | 0 | 37195 | 36 | 4320 | 216 | 5700 |  | 1800 | 0 | 12036 | 30 | 3600 | 180 | 1650 |  | 7550 | 0 | 12980 | 38 | 4560 | 228 | 4201 |  | 3190 | 0 | 12179 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 2640 | 132 | 0 |  | 2400 | 0 | 5172 | 14 | 1680 | 84 | 0 |  | 0 | 0 | 1764 | 4 | 480 | 24 | 0 |  | 1200 | 0 | 1704 | 4 | 480 | 24 | 0 |  | 1200 | 0 | 1704 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 360 | 18 |  |  |  |  | 378 | 3 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 120 | 6 |  | Ext. Meeting Organisation | 1200 |  | 1326 | 1 | 120 | 6 |  | Ext. Meeting Organisation |  |  | 126 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 960 | 48 |  | Ext. Meeting Organisation | 1200 |  | 2208 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 480 | 24 |  | Ext. Meeting Organisation | 600 |  | 1104 | 4 | 480 | 24 |  | Ext. Meeting Organisation | 600 |  | 1104 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 240 | 12 |  |  |  |  | 252 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 480 | 24 |  |  |  |  | 504 | 4 | 480 | 24 |  |  |  |  | 504 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 480 | 24 | 0 |  | 6000 | 2000 | 8504 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 480 | 24 | 0 |  | 0 | 0 | 504 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 | 2 | 240 | 12 |  |  |  |  | 252 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 240 | 12 |  | Ext. Project Coordination | 6000 | 2000 | 8252 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 240 | 12 |  | Ext. Project Coordination |  |  | 252 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 1200 | 60 | 0 |  | 0 | 0 | 1260 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 600 | 30 | 0 |  | 0 | 0 | 630 | 5 | 600 | 30 | 0 |  | 0 | 0 | 630 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 600 | 30 |  |  |  |  | 630 |  | 0 | 0 |  |  |  |  | 0 | 5 | 600 | 30 |  |  |  |  | 630 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 600 | 30 |  |  |  |  | 630 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 600 | 30 |  |  |  |  | 630 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 1440 | 72 | 0 |  | 1000 | 0 | 2512 | 3.2 | 384 | 19.2 | 0 |  | 0 | 0 | 403.2 | 2.4 | 288 | 14.4 | 0 |  | 500 | 0 | 802.4 | 6.4 | 768 | 38.4 | 0 |  | 500 | 0 | 1306.4 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 120 | 6 |  |  |  |  | 126 | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 720 | 36 |  |  |  |  | 756 | 1.2 | 144 | 7.2 |  |  |  |  | 151.2 | 2.4 | 288 | 14.4 |  |  |  |  | 302.4 | 2.4 | 288 | 14.4 |  |  |  |  | 302.4 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 120 | 6 |  |  |  |  | 126 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 120 | 6 |  |  |  |  | 126 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 360 | 18 |  |  |  |  | 378 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 5760 | 288 | 0 |  | 9400 | 2000 | 17448 | 17.2 | 2064 | 103.2 | 0 |  | 0 | 0 | 2167.2 | 15.4 | 1848 | 92.4 | 0 |  | 1700 | 0 | 3640.4 | 15.4 | 1848 | 92.4 | 0 |  | 7700 | 2000 | 11640.4 | OK
|  |  |  | 173 | 20760 | 1038 | 11551 |  | 26940 | 2000 | 62289 | 173 | 7224 | 361.2 | 5700 |  | 2800 | 0 | 16085.2 | 20760 | 6168 | 308.4 | 1650 |  | 11250 | 0 | 19376.4 | 0 | 7368 | 368.4 | 4201 |  | 12890 | 2000 | 26827.4 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 20760 | 7224 | 6168 | 7368 |  | OK
|  | Total |  | 20760 | 7224 | 6168 | 7368 |  | OK
| Office and Admin | Office and Administration |  | 1038 | 361.2 | 308.4 | 368.4 |  | OK
|  | Total |  | 1038 | 361.2 | 308.4 | 368.4 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11551 | 5700 | 1650 | 4201 |  | OK
|  | Total |  | 11551 | 5700 | 1650 | 4201 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 11000 | 1000 | 2000 | 8000 |  | OK
|  | Ext. Meeting Organisation |  | 8400 | 0 | 7200 | 1200 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 6540 | 1800 | 1550 | 3190 |  | OK
|  | First Level Control |  | 0 | 0 | 0 | 0 |  | OK
|  | Total |  | 26940 | 2800 | 11250 | 12890 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 62289 | 16085.2 | 19376.4 | 26827.4 |  | OK
62289
|  |  | CHECK | OK | OK | OK | OK

## P7_OUL
P7 | Oulu |  |  | Country | FI |  | Total Budget |  |  |  | 87512.5 | 2023 | [5 empty] | Budget 2023 | 24902.5 | 2024 | [5 empty] | Budget 2024 | 21992.5 | 2025 | [5 empty] | Budget 2025 | 40617.5 | OK
|  |  |  | Daily rate | 250 |  | ERDF |  |  | 70% | 61258.75 | [6 empty] | ERDF | 17431.75 | [6 empty] | ERDF | 15394.75 | [6 empty] | ERDF | 28432.25 | OK
[7 empty] | National Co-financing |  |  | 30% | 26253.75 | [6 empty] | Nat. Co-fin | 7470.75 | [6 empty] | Nat. Co-fin | 6597.75 | [6 empty] | Nat. Co-fin | 12185.25 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 2250 | 112.5 | 0 |  | 0 | 0 | 2362.5 | 5 | 1250 | 62.5 | 0 |  | 0 | 0 | 1312.5 | 2 | 500 | 25 | 0 |  | 0 | 0 | 525 | 2 | 500 | 25 | 0 |  | 0 | 0 | 525 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 250 | 12.5 |  |  |  | 0 | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 1250 | 62.5 |  |  |  |  | 1312.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 750 | 37.5 | 0 |  | 0 | 0 | 787.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 250 | 12.5 | 0 |  | 0 | 0 | 262.5 | 2 | 500 | 25 | 0 |  | 0 | 0 | 525 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 2250 | 112.5 | 0 |  | 0 | 0 | 2362.5 | 2 | 500 | 25 | 0 |  | 0 | 0 | 525 | 3 | 750 | 37.5 | 0 |  | 0 | 0 | 787.5 | 4 | 1000 | 50 | 0 |  | 0 | 0 | 1050 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1500 | 75 |  |  |  |  | 1575 | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 5250 | 262.5 | 0 |  | 0 | 0 | 5512.5 | 7 | 1750 | 87.5 | 0 |  | 0 | 0 | 1837.5 | 6 | 1500 | 75 | 0 |  | 0 | 0 | 1575 | 8 | 2000 | 100 | 0 |  | 0 | 0 | 2100 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 21750 | 1087.5 | 14800 |  | 14300 | 0 | 51937.5 | 29 | 7250 | 362.5 | 7100 |  | 2000 | 0 | 16712.5 | 29 | 7250 | 362.5 | 3000 |  | 3000 | 0 | 13612.5 | 29 | 7250 | 362.5 | 4700 |  | 9300 | 0 | 21612.5 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 1000 | 50 |  |  |  |  | 1050 | 4 | 1000 | 50 | 0 |  |  |  | 1050 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 750 | 37.5 |  |  |  |  | 787.5 | 3 | 750 | 37.5 | 0 |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 2000 | 100 | 2100 | Exp. & non-staff Travel | 1000 |  | 5200 | 8 | 2000 | 100 | 2100 | Exp. & non-staff Travel | 1000 |  | 5200 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 1500 | 75 | 2200 | Exp. & non-staff Travel | 1000 |  | 4775 | 6 | 1500 | 75 | 2200 | Exp. & non-staff Travel | 1000 |  | 4775 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 1500 | 75 | 1300 | Exp. & non-staff Travel | 1300 |  | 4175 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 1300 | Exp. & non-staff Travel | 1300 |  | 4175 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 1500 | 75 | 800 | Exp. & non-staff Travel | 800 |  | 3175 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 800 | Exp. & non-staff Travel | 800 |  | 3175 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 1500 | 75 | 900 | Exp. & non-staff Travel | 900 |  | 3375 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 900 | Exp. & non-staff Travel | 900 |  | 3375 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 1500 | 75 | 0 |  |  |  | 1575 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1500 | 75 | 0 |  | 0 |  | 1575 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 1500 | 75 | 0 | Ext. Meeting Organisation | 6000 |  | 7575 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 1500 | 75 | 0 | Ext. Meeting Organisation | 6000 |  | 7575 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 1500 | 75 | 1200 | Exp. & non-staff Travel | 1200 |  | 3975 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 1200 | Exp. & non-staff Travel | 1200 |  | 3975 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 1500 | 75 | 2400 | Exp. & non-staff Travel | 1100 |  | 5075 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 2400 | Exp. & non-staff Travel | 1100 |  | 5075 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 1500 | 75 | 1100 | Exp. & non-staff Travel | 1000 |  | 3675 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1500 | 75 | 1100 | Exp. & non-staff Travel | 1000 |  | 3675 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 1500 | 75 |  |  |  |  | 1575 | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 1500 | 75 |  |  |  |  | 1575 |  | 0 | 0 |  |  |  |  | 0 | 3 | 750 | 37.5 |  |  |  |  | 787.5 | 3 | 750 | 37.5 |  |  |  |  | 787.5 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 1500 | 75 | 2800 |  |  |  | 4375 | 6 | 1500 | 75 | 2800 |  |  |  | 4375 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 4250 | 212.5 | 0 |  | 0 | 0 | 4462.5 | 7 | 1750 | 87.5 | 0 |  | 0 | 0 | 1837.5 | 1 | 250 | 12.5 | 0 |  | 0 | 0 | 262.5 | 9 | 2250 | 112.5 | 0 |  | 0 | 0 | 2362.5 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 750 | 37.5 |  |  |  |  | 787.5 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1500 | 75 |  |  |  |  | 1575 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1500 | 75 |  |  |  |  | 1575 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 26000 | 1300 | 14800 |  | 14300 | 0 | 56400 | 36 | 9000 | 450 | 7100 |  | 2000 | 0 | 18550 | 30 | 7500 | 375 | 3000 |  | 3000 | 0 | 13875 | 38 | 9500 | 475 | 4700 |  | 9300 | 0 | 23975 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 5500 | 275 | 0 |  | 4000 | 0 | 9775 | 14 | 3500 | 175 | 0 |  | 0 | 0 | 3675 | 4 | 1000 | 50 | 0 |  | 2000 | 0 | 3050 | 4 | 1000 | 50 | 0 |  | 2000 | 0 | 3050 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 750 | 37.5 |  |  |  |  | 787.5 | 3 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 250 | 12.5 |  | Ext. Meeting Organisation | 2400 |  | 2662.5 | 1 | 250 | 12.5 |  | Ext. Meeting Organisation |  |  | 262.5 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 2000 | 100 |  | Ext. Meeting Organisation | 1600 |  | 3700 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 1000 | 50 |  | Ext. Meeting Organisation | 800 |  | 1850 | 4 | 1000 | 50 |  | Ext. Meeting Organisation | 800 |  | 1850 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 500 | 25 |  |  |  |  | 525 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 1000 | 50 |  |  |  |  | 1050 | 4 | 1000 | 50 |  |  |  |  | 1050 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 1000 | 50 | 0 |  | 6000 | 2000 | 9050 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 1000 | 50 | 0 |  | 0 | 0 | 1050 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 | 2 | 500 | 25 |  |  |  |  | 525 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 500 | 25 |  | Ext. Project Coordination | 6000 | 2000 | 8525 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 500 | 25 |  | Ext. Project Coordination |  |  | 525 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 2500 | 125 | 0 |  | 0 | 0 | 2625 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 1250 | 62.5 | 0 |  | 0 | 0 | 1312.5 | 5 | 1250 | 62.5 | 0 |  | 0 | 0 | 1312.5 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 1250 | 62.5 |  |  |  |  | 1312.5 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1250 | 62.5 |  |  |  |  | 1312.5 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 1250 | 62.5 |  |  |  |  | 1312.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 1250 | 62.5 |  |  |  |  | 1312.5 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 3000 | 150 | 0 |  | 1000 | 0 | 4150 | 3.2 | 800 | 40 | 0 |  | 0 | 0 | 840 | 2.4 | 600 | 30 | 0 |  | 500 | 0 | 1130 | 6.4 | 1600 | 80 | 0 |  | 500 | 0 | 2180 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 250 | 12.5 |  |  |  |  | 262.5 | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1500 | 75 |  |  |  |  | 1575 | 1.2 | 300 | 15 |  |  |  |  | 315 | 2.4 | 600 | 30 |  |  |  |  | 630 | 2.4 | 600 | 30 |  |  |  |  | 630 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 250 | 12.5 |  |  |  |  | 262.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 250 | 12.5 |  |  |  |  | 262.5 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 750 | 37.5 |  |  |  |  | 787.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 750 | 37.5 |  |  |  |  | 787.5 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 12000 | 600 | 0 |  | 11000 | 2000 | 25600 | 17.2 | 4300 | 215 | 0 |  | 0 | 0 | 4515 | 15.4 | 3850 | 192.5 | 0 |  | 2500 | 0 | 6542.5 | 15.4 | 3850 | 192.5 | 0 |  | 8500 | 2000 | 14542.5 | OK
|  |  |  | 173 | 43250 | 2162.5 | 14800 |  | 25300 | 2000 | 87512.5 | 173 | 15050 | 752.5 | 7100 |  | 2000 | 0 | 24902.5 | 20760 | 12850 | 642.5 | 3000 |  | 5500 | 0 | 21992.5 | 0 | 15350 | 767.5 | 4700 |  | 17800 | 2000 | 40617.5 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 43250 | 15050 | 12850 | 15350 |  | OK
|  | Total |  | 43250 | 15050 | 12850 | 15350 |  | OK
| Office and Admin | Office and Administration |  | 2162.5 | 752.5 | 642.5 | 767.5 |  | OK
|  | Total |  | 2162.5 | 752.5 | 642.5 | 767.5 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 14800 | 7100 | 3000 | 4700 |  | OK
|  | Total |  | 14800 | 7100 | 3000 | 4700 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 10000 | 0 | 2000 | 8000 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 8300 | 2000 | 3000 | 3300 |  | OK
|  | First Level Control |  | 0 | 0 | 0 | 0 |  | OK
|  | Total |  | 25300 | 2000 | 5500 | 17800 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 87512.5 | 24902.5 | 21992.5 | 40617.5 |  | OK
87512.5
|  |  | CHECK | OK | OK | OK | OK

## P8_PER
P8 | Perugia |  |  | Country | IT |  | Total Budget |  |  |  | 70997 | 2023 | [5 empty] | Budget 2023 | 19477.8 | 2024 | [5 empty] | Budget 2024 | 16914.6 | 2025 | [5 empty] | Budget 2025 | 34604.6 | OK
|  |  |  | Daily rate | 180 |  | ERDF |  |  | 70% | 49697.9 | [6 empty] | ERDF | 13634.46 | [6 empty] | ERDF | 11840.22 | [6 empty] | ERDF | 24223.22 | OK
[7 empty] | National Co-financing |  |  | 30% | 21299.1 | [6 empty] | Nat. Co-fin | 5843.34 | [6 empty] | Nat. Co-fin | 5074.38 | [6 empty] | Nat. Co-fin | 10381.38 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 180 | 9 |  |  |  | 0 | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 900 | 45 |  |  |  |  | 945 | 1 | 180 | 9 |  |  |  |  | 189 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1620 | 81 | 0 |  | 1500 | 0 | 3201 | 2 | 360 | 18 | 0 |  | 500 | 0 | 878 | 3 | 540 | 27 | 0 |  | 500 | 0 | 1067 | 4 | 720 | 36 | 0 |  | 500 | 0 | 1256 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1080 | 54 |  | First Level Control | 1500 |  | 2634 | 2 | 360 | 18 |  | First Level Control | 500 |  | 878 | 2 | 360 | 18 |  | First Level Control | 500 |  | 878 | 2 | 360 | 18 |  | First Level Control | 500 |  | 878 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 3780 | 189 | 0 |  | 1500 | 0 | 5469 | 7 | 1260 | 63 | 0 |  | 500 | 0 | 1823 | 6 | 1080 | 54 | 0 |  | 500 | 0 | 1634 | 8 | 1440 | 72 | 0 |  | 500 | 0 | 2012 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 15660 | 783 | 11250 |  | 12550 | 0 | 40243 | 29 | 5220 | 261 | 5900 |  | 1700 | 0 | 13081 | 29 | 5220 | 261 | 2050 |  | 2150 | 0 | 9681 | 29 | 5220 | 261 | 3300 |  | 8700 | 0 | 17481 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 | 0 |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 | 0 |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 1440 | 72 | 1700 | Exp. & non-staff Travel | 800 |  | 4012 | 8 | 1440 | 72 | 1700 | Exp. & non-staff Travel | 800 |  | 4012 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 1080 | 54 | 2000 | Exp. & non-staff Travel | 900 |  | 4034 | 6 | 1080 | 54 | 2000 | Exp. & non-staff Travel | 900 |  | 4034 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 750 | Exp. & non-staff Travel | 750 |  | 2634 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 1080 | 54 | 0 |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 | 0 |  | 0 |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 1080 | 54 | 700 | Exp. & non-staff Travel | 700 |  | 2534 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 700 | Exp. & non-staff Travel | 700 |  | 2534 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 700 |  | 2434 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 700 |  | 2434 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 1080 | 54 | 1300 | Exp. & non-staff Travel | 1300 |  | 3734 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1300 | Exp. & non-staff Travel | 1300 |  | 3734 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 1080 | 54 | 0 | Ext. Meeting Organisation | 6000 |  | 7134 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 1080 | 54 | 1400 | Exp. & non-staff Travel | 800 |  | 3334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 1400 | Exp. & non-staff Travel | 800 |  | 3334 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 600 |  | 2334 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 1080 | 54 | 600 | Exp. & non-staff Travel | 600 |  | 2334 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 1080 | 54 | 2200 |  |  |  | 3334 | 6 | 1080 | 54 | 2200 |  |  |  | 3334 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 3060 | 153 | 0 |  | 0 | 0 | 3213 | 7 | 1260 | 63 | 0 |  | 0 | 0 | 1323 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 |  |  |  |  | 1134 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 18720 | 936 | 11250 |  | 12550 | 0 | 43456 | 36 | 6480 | 324 | 5900 |  | 1700 | 0 | 14404 | 30 | 5400 | 270 | 2050 |  | 2150 | 0 | 9870 | 38 | 6840 | 342 | 3300 |  | 8700 | 0 | 19182 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 3960 | 198 | 0 |  | 4000 | 0 | 8158 | 14 | 2520 | 126 | 0 |  | 0 | 0 | 2646 | 4 | 720 | 36 | 0 |  | 2000 | 0 | 2756 | 4 | 720 | 36 | 0 |  | 2000 | 0 | 2756 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Meeting Organisation | 2400 |  | 2589 | 1 | 180 | 9 |  | Ext. Meeting Organisation |  |  | 189 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 |  | 0 | 0 |  | Ext. Meeting Organisation | 1200 |  | 1200 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 1440 | 72 |  | Ext. Meeting Organisation | 1600 |  | 3112 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 800 |  | 1556 | 4 | 720 | 36 |  | Ext. Meeting Organisation | 800 |  | 1556 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 720 | 36 |  |  |  |  | 756 | 4 | 720 | 36 |  |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 720 | 36 | 0 |  | 6000 | 2000 | 8756 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 720 | 36 | 0 |  | 0 | 0 | 756 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 360 | 18 |  | Ext. Project Coordination | 6000 | 2000 | 8378 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 360 | 18 |  | Ext. Project Coordination |  |  | 378 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 1800 | 90 | 0 |  | 0 | 0 | 1890 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 900 | 45 |  |  |  |  | 945 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 900 | 45 |  |  |  |  | 945 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 2160 | 108 | 0 |  | 1000 | 0 | 3268 | 3.2 | 576 | 28.8 | 0 |  | 0 | 0 | 604.8 | 2.4 | 432 | 21.6 | 0 |  | 500 | 0 | 953.6 | 6.4 | 1152 | 57.6 | 0 |  | 500 | 0 | 1709.6 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1080 | 54 |  |  |  |  | 1134 | 1.2 | 216 | 10.8 |  |  |  |  | 226.8 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 8640 | 432 | 0 |  | 11000 | 2000 | 22072 | 17.2 | 3096 | 154.8 | 0 |  | 0 | 0 | 3250.8 | 15.4 | 2772 | 138.6 | 0 |  | 2500 | 0 | 5410.6 | 15.4 | 2772 | 138.6 | 0 |  | 8500 | 2000 | 13410.6 | OK
|  |  |  | 173 | 31140 | 1557 | 11250 |  | 25050 | 2000 | 70997 | 173 | 10836 | 541.8 | 5900 |  | 2200 | 0 | 19477.8 | 20760 | 9252 | 462.6 | 2050 |  | 5150 | 0 | 16914.6 | 0 | 11052 | 552.6 | 3300 |  | 17700 | 2000 | 34604.6 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 31140 | 10836 | 9252 | 11052 |  | OK
|  | Total |  | 31140 | 10836 | 9252 | 11052 |  | OK
| Office and Admin | Office and Administration |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
|  | Total |  | 1557 | 541.8 | 462.6 | 552.6 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11250 | 5900 | 2050 | 3300 |  | OK
|  | Total |  | 11250 | 5900 | 2050 | 3300 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 10000 | 0 | 2000 | 8000 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 6550 | 1700 | 2150 | 2700 |  | OK
|  | First Level Control |  | 1500 | 500 | 500 | 500 |  | OK
|  | Total |  | 25050 | 2200 | 5150 | 17700 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 70997 | 19477.8 | 16914.6 | 34604.6 |  | OK
70997
|  |  | CHECK | OK | OK | OK | OK

## P10_VIL
P10 | Viladecans |  |  | Country | ES |  | Total Budget |  |  |  | 75283 | 2023 | [5 empty] | Budget 2023 | 19941.8 | 2024 | [5 empty] | Budget 2024 | 19255.6 | 2025 | [5 empty] | Budget 2025 | 36085.6 | OK
|  |  |  | Daily rate | 180 |  | ERDF |  |  | 65% | 48933.95 | [6 empty] | ERDF | 12962.17 | [6 empty] | ERDF | 12516.14 | [6 empty] | ERDF | 23455.64 | OK
[7 empty] | National Co-financing |  |  | 35% | 26349.05 | [6 empty] | Nat. Co-fin | 6979.63 | [6 empty] | Nat. Co-fin | 6739.46 | [6 empty] | Nat. Co-fin | 12629.96 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | 5 | 900 | 45 | 0 |  | 0 | 0 | 945 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 180 | 9 |  |  |  | 0 | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 900 | 45 |  |  |  |  | 945 | 1 | 180 | 9 |  |  |  |  | 189 | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 2 | 360 | 18 | 0 |  | 0 | 0 | 378 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 1620 | 81 | 0 |  | 2400 | 0 | 4101 | 2 | 360 | 18 | 0 |  | 800 | 0 | 1178 | 3 | 540 | 27 | 0 |  | 800 | 0 | 1367 | 4 | 720 | 36 | 0 |  | 800 | 0 | 1556 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 1080 | 54 |  | First Level Control | 2400 |  | 3534 | 2 | 360 | 18 |  | First Level Control | 800 |  | 1178 | 2 | 360 | 18 |  | First Level Control | 800 |  | 1178 | 2 | 360 | 18 |  | First Level Control | 800 |  | 1178 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 3780 | 189 | 0 |  | 2400 | 0 | 6369 | 7 | 1260 | 63 | 0 |  | 800 | 0 | 2123 | 6 | 1080 | 54 | 0 |  | 800 | 0 | 1934 | 8 | 1440 | 72 | 0 |  | 800 | 0 | 2312 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 59 | 10620 | 531 | 11000 |  | 18240 | 0 | 40391 | 20 | 3600 | 180 | 5800 |  | 3008 | 0 | 12588 | 20 | 3600 | 180 | 3400 |  | 5216 | 0 | 12396 | 19 | 3420 | 171 | 1800 |  | 10016 | 0 | 15407 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 3 | 540 | 27 |  |  |  |  | 567 | 3 | 540 | 27 | 0 |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 | 0 |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 6 | 1080 | 54 | 1600 | Exp. & non-staff Travel | 900 |  | 3634 | 6 | 1080 | 54 | 1600 | Exp. & non-staff Travel | 900 |  | 3634 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 4 | 720 | 36 | 2000 | Exp. & non-staff Travel | 1100 |  | 3856 | 4 | 720 | 36 | 2000 | Exp. & non-staff Travel | 1100 |  | 3856 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 4 | 720 | 36 | 1400 | Exp. & non-staff Travel | 800 |  | 2956 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 1400 | Exp. & non-staff Travel | 800 |  | 2956 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 4 | 720 | 36 | 700 | Exp. & non-staff Travel | 800 |  | 2256 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 700 | Exp. & non-staff Travel | 800 |  | 2256 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 4 | 720 | 36 | 800 | Exp. & non-staff Travel | 800 |  | 2356 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 800 | Exp. & non-staff Travel | 800 |  | 2356 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 4 | 720 | 36 | 500 | Exp. & non-staff Travel | 800 |  | 2056 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 500 | Exp. & non-staff Travel | 800 |  | 2056 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 4 | 720 | 36 | 1200 | Exp. & non-staff Travel | 1400 |  | 3356 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 1200 | Exp. & non-staff Travel | 1400 |  | 3356 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 4 | 720 | 36 | 0 |  |  |  | 756 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 4 | 720 | 36 | 0 |  | 0 |  | 756 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 4 | 720 | 36 | 0 | Ext. Meeting Organisation | 6000 |  | 6756 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 720 | 36 | 0 | Ext. Meeting Organisation | 6000 |  | 6756 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 4 | 720 | 36 | 600 | Exp. & non-staff Travel | 600 |  | 1956 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 4 | 720 | 36 | 600 | Exp. & non-staff Travel | 600 |  | 1956 | OK
2.1.13 | Staff Exchanges |  | All PPs | 4 | 720 | 36 |  |  |  |  | 756 | 1 | 180 | 9 |  |  |  |  | 189 | 2 | 360 | 18 |  |  |  |  | 378 | 1 | 180 | 9 |  |  |  |  | 189 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 4 | 720 | 36 |  | Ext. Project Coordination | 5040 |  | 5796 |  | 0 | 0 |  | Ext. Project Coordination | 1008 |  | 1008 | 2 | 360 | 18 |  | Ext. Project Coordination | 2016 |  | 2394 | 2 | 360 | 18 |  | Ext. Project Coordination | 2016 |  | 2394 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 4 | 720 | 36 | 2200 |  |  |  | 2956 | 4 | 720 | 36 | 2200 |  |  |  | 2956 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 3060 | 153 | 0 |  | 0 | 0 | 3213 | 7 | 1260 | 63 | 0 |  | 0 | 0 | 1323 | 1 | 180 | 9 | 0 |  | 0 | 0 | 189 | 9 | 1620 | 81 | 0 |  | 0 | 0 | 1701 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 360 | 18 |  |  |  |  | 378 | 2 | 360 | 18 |  |  |  |  | 378 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 1080 | 54 |  |  |  |  | 1134 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 1080 | 54 |  |  |  |  | 1134 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 76 | 13680 | 684 | 11000 |  | 18240 | 0 | 43604 | 27 | 4860 | 243 | 5800 |  | 3008 | 0 | 13911 | 21 | 3780 | 189 | 3400 |  | 5216 | 0 | 12585 | 28 | 5040 | 252 | 1800 |  | 10016 | 0 | 17108 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 11 | 1980 | 99 | 0 |  | 6180 | 0 | 8259 | 7 | 1260 | 63 | 0 |  | 1980 | 0 | 3303 | 2 | 360 | 18 | 0 |  | 2100 | 0 | 2478 | 2 | 360 | 18 | 0 |  | 2100 | 0 | 2478 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Meeting Organisation | 2100 |  | 2289 | 1 | 180 | 9 |  | Ext. Meeting Organisation |  |  | 189 |  | 0 | 0 |  | Ext. Meeting Organisation | 1050 |  | 1050 |  | 0 | 0 |  | Ext. Meeting Organisation | 1050 |  | 1050 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 4 | 720 | 36 |  | Ext. Meeting Organisation | 2100 |  | 2856 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 2 | 360 | 18 |  | Ext. Meeting Organisation | 1050 |  | 1428 | 2 | 360 | 18 |  | Ext. Meeting Organisation | 1050 |  | 1428 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 2 | 360 | 18 |  | Ext. Project Coordination | 1980 |  | 2358 | 2 | 360 | 18 |  | Ext. Project Coordination | 1980 |  | 2358 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 2 | 360 | 18 | 0 |  | 6360 | 2000 | 8738 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2 | 360 | 18 | 0 |  | 360 | 0 | 738 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Project Coordination | 360 |  | 549 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 1 | 180 | 9 |  | Ext. Project Coordination | 360 |  | 549 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 1 | 180 | 9 |  | Ext. Project Coordination | 6000 | 2000 | 8189 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 1 | 180 | 9 |  | Ext. Project Coordination |  |  | 189 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 5 | 900 | 45 | 0 |  | 4100 | 0 | 5045 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 3 | 540 | 27 | 0 |  | 0 | 0 | 567 | 2 | 360 | 18 | 0 |  | 4100 | 0 | 4478 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 2 | 360 | 18 |  | Ext. Project Coordination | 4100 |  | 4478 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 360 | 18 |  | Ext. Project Coordination | 4100 |  | 4478 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 2160 | 108 | 0 |  | 1000 | 0 | 3268 | 3.2 | 576 | 28.8 | 0 |  | 0 | 0 | 604.8 | 2.4 | 432 | 21.6 | 0 |  | 500 | 0 | 953.6 | 6.4 | 1152 | 57.6 | 0 |  | 500 | 0 | 1709.6 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 1080 | 54 |  |  |  |  | 1134 | 1.2 | 216 | 10.8 |  |  |  |  | 226.8 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | 2.4 | 432 | 21.6 |  |  |  |  | 453.6 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 180 | 9 |  |  |  |  | 189 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 180 | 9 |  |  |  |  | 189 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 540 | 27 |  |  |  |  | 567 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 540 | 27 |  |  |  |  | 567 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 30 | 5400 | 270 | 0 |  | 17640 | 2000 | 25310 | 10.2 | 1836 | 91.8 | 0 |  | 1980 | 0 | 3907.8 | 9.4 | 1692 | 84.6 | 0 |  | 2960 | 0 | 4736.6 | 10.4 | 1872 | 93.6 | 0 |  | 12700 | 2000 | 16665.6 | OK
|  |  |  | 127 | 22860 | 1143 | 11000 |  | 38280 | 2000 | 75283 | 173 | 7956 | 397.8 | 5800 |  | 5788 | 0 | 19941.8 | 20760 | 6552 | 327.6 | 3400 |  | 8976 | 0 | 19255.6 | 0 | 8352 | 417.6 | 1800 |  | 23516 | 2000 | 36085.6 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 22860 | 7956 | 6552 | 8352 |  | OK
|  | Total |  | 22860 | 7956 | 6552 | 8352 |  | OK
| Office and Admin | Office and Administration |  | 1143 | 397.8 | 327.6 | 417.6 |  | OK
|  | Total |  | 1143 | 397.8 | 327.6 | 417.6 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11000 | 5800 | 3400 | 1800 |  | OK
|  | Total |  | 11000 | 5800 | 3400 | 1800 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 17480 | 2988 | 2376 | 12116 |  | OK
|  | Ext. Meeting Organisation |  | 10200 | 0 | 2100 | 8100 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 7200 | 2000 | 3200 | 2000 |  | OK
|  | First Level Control |  | 2400 | 800 | 800 | 800 |  | OK
|  | Total |  | 38280 | 5788 | 8976 | 23516 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 75283 | 19941.8 | 19255.6 | 36085.6 |  | OK
75283
|  |  | CHECK | OK | OK | OK | OK

## P9_TET
P9 | Тetovo |  |  | Country | MK |  | Total Budget |  |  |  | 49340.25 | 2023 | [5 empty] | Budget 2023 | 13272.85 | 2024 | [5 empty] | Budget 2024 | 10487.45 | 2025 | [5 empty] | Budget 2025 | 25579.95 | OK
|  |  |  | Daily rate | 85 |  | IPA |  |  | 95% | 46873.2375 | [6 empty] | IPA | 12609.2075 | [6 empty] | IPA | 9963.0775 | [6 empty] | IPA | 24300.9525 | OK
[7 empty] | National Co-financing |  |  | 5% | 2467.0125 | [6 empty] | Nat. Co-fin | 663.6425 | [6 empty] | Nat. Co-fin | 524.3725 | [6 empty] | Nat. Co-fin | 1278.9975 | OK
Action | Activity | Partner in charge | Participating | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL | Staff |  | Overhead | Travel and accomm. | External expertise |  | Equipment | TOTAL
|  |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost |  |  | Days | Cost |  |  | Category | Cost
WP1 | NETWORK MANAGEMENT
1.1 | Start-up and overall coordination |  |  | 9 | 765 | 38.25 | 0 |  | 0 | 0 | 803.25 | 5 | 425 | 21.25 | 0 |  | 0 | 0 | 446.25 | 2 | 170 | 8.5 | 0 |  | 0 | 0 | 178.5 | 2 | 170 | 8.5 | 0 |  | 0 | 0 | 178.5 | OK
1.1.1 | Signature of the Subsidy Contract | LP |  | 1 | 85 | 4.25 |  |  |  | 0 | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.2 | Signature of the Joint Convention | LP | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.3 | Setting up project teams: project coordinator, ULG coordinator, comm. officer, | LP | All PPs | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.1.4 | Overall project and financial management (incl. the network and ad-hoc expert) | LP | All PPs | 5 | 425 | 21.25 |  |  |  |  | 446.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | OK
1.1.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2 | Coordination meetings and mid-term reflection |  |  | 3 | 255 | 12.75 | 0 |  | 0 | 0 | 267.75 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 85 | 4.25 | 0 |  | 0 | 0 | 89.25 | 2 | 170 | 8.5 | 0 |  | 0 | 0 | 178.5 | OK
1.2.1 | Coordination meetings of project coordinators linked to the partner meetings | LP | All PPs | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.2 | Online coordination meetings | LP/LE | All PPs | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | OK
1.2.3 | Mid-term reflection and if needed, Reprogramming Procedure | LP/LE | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | OK
1.2.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.2.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3 | Reporting and project closure |  |  | 9 | 765 | 38.25 | 0 |  | 0 | 0 | 803.25 | 2 | 170 | 8.5 | 0 |  | 0 | 0 | 178.5 | 3 | 255 | 12.75 | 0 |  | 0 | 0 | 267.75 | 4 | 340 | 17 | 0 |  | 0 | 0 | 357 | OK
1.3.1 | Partner level reports (incl. Identification and approval of FLCs) | All PPs |  | 6 | 510 | 25.5 |  |  |  |  | 535.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | OK
1.3.2 | Project level reports: Payment Claim, Evidence Package, Progress Report | LP | All PPs | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | OK
1.3.3 | Closure Report | LP | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | OK
1.3.4 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
1.3.5 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 21 | 1785 | 89.25 | 0 |  | 0 | 0 | 1874.25 | 7 | 595 | 29.75 | 0 |  | 0 | 0 | 624.75 | 6 | 510 | 25.5 | 0 |  | 0 | 0 | 535.5 | 8 | 680 | 34 | 0 |  | 0 | 0 | 714 | OK
WP2 | TRANSNATIONAL ACTIVITIES |  |  | 0 | [31 empty] | OK
2.1 | Transnational Activities |  |  | 87 | 7395 | 369.75 | 11750 |  | 10750 | 0 | 30264.75 | 29 | 2465 | 123.25 | 6000 |  | 1900 | 0 | 10488.25 | 29 | 2465 | 123.25 | 2100 |  | 2100 | 0 | 6788.25 | 29 | 2465 | 123.25 | 3650 |  | 6750 | 0 | 12988.25 | OK
2.1.1 | Programme level kick-off meeting | All PPs |  | 4 | 340 | 17 |  |  |  |  | 357 | 4 | 340 | 17 | 0 |  |  |  | 357 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.2 | Baseline Study process: City Visits | LP/LE | All PPs | 3 | 255 | 12.75 |  |  |  |  | 267.75 | 3 | 255 | 12.75 | 0 |  |  |  | 267.75 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.3 | CTM 01: Project level kick-off meeting (CORE) | Eindhoven | All PPs | 8 | 680 | 34 | 1600 | Exp. & non-staff Travel | 900 |  | 3214 | 8 | 680 | 34 | 1600 | Exp. & non-staff Travel | 900 |  | 3214 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.4 | CTM 02: Ready for Action Meeting (CORE) | Aarhus | All PPs | 6 | 510 | 25.5 | 2100 | Exp. & non-staff Travel | 1000 |  | 3635.5 | 6 | 510 | 25.5 | 2100 | Exp. & non-staff Travel | 1000 |  | 3635.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.5 | CTM 03: Integrated Approach Meeting (CORE) | Cartagena | All PPs | 6 | 510 | 25.5 | 800 | Exp. & non-staff Travel | 800 |  | 2135.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 800 | Exp. & non-staff Travel | 800 |  | 2135.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.6 | OTM 04: Planning SSAs | Gdańsk | optional | 6 | 510 | 25.5 | 650 | Exp. & non-staff Travel | 650 |  | 1835.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 650 | Exp. & non-staff Travel | 650 |  | 1835.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.7 | OTM 05: Going Cross-Sectoral. Digital, Gender, Green | Iași | optional | 6 | 510 | 25.5 | 0 |  |  |  | 535.5 |  | 0 | 0 |  |  |  |  | 0 | 6 | 510 | 25.5 | 0 |  | 0 |  | 535.5 |  | 0 | 0 |  |  |  |  | 0 | OK
2.1.8 | OTM 06: Capacity Building of Civil Servants | Veszprém | optional | 6 | 510 | 25.5 | 650 | Exp. & non-staff Travel | 650 |  | 1835.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 650 | Exp. & non-staff Travel | 650 |  | 1835.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | OK
2.1.9 | CTM 07: IAP Draft Peer Review (CORE) | Oulu | All PPs | 6 | 510 | 25.5 | 1300 | Exp. & non-staff Travel | 1300 |  | 3135.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 1300 | Exp. & non-staff Travel | 1300 |  | 3135.5 | OK
2.1.10 | OTM 08: Lessons Learnt from SSAs | Perugia | optional | 6 | 510 | 25.5 | 750 | Exp. & non-staff Travel | 750 |  | 2035.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 750 | Exp. & non-staff Travel | 750 |  | 2035.5 | OK
2.1.11 | CTM 09: Final IAP Peer Review (CORE) | Viladecans | All PPs | 6 | 510 | 25.5 | 1600 | Exp. & non-staff Travel | 700 |  | 2835.5 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 |  | 0 | 0 |  | Exp. & non-staff Travel |  |  | 0 | 6 | 510 | 25.5 | 1600 | Exp. & non-staff Travel | 700 |  | 2835.5 | OK
2.1.12 | CTM 10: Final Meeting (CORE) | Тetovo | All PPs | 6 | 510 | 25.5 | 0 | Ext. Meeting Organisation | 4000 |  | 4535.5 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 6 | 510 | 25.5 | 0 | Ext. Meeting Organisation | 4000 |  | 4535.5 | OK
2.1.13 | Staff Exchanges |  | All PPs | 6 | 510 | 25.5 |  |  |  |  | 535.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 | OK
2.1.14 | Quarterly Network Reports, Good Practice Catalogue | LE | All PPs | 6 | 510 | 25.5 |  |  |  |  | 535.5 |  | 0 | 0 |  |  |  |  | 0 | 3 | 255 | 12.75 |  |  |  |  | 267.75 | 3 | 255 | 12.75 |  |  |  |  | 267.75 | OK
2.1.15 | Urbact Summer University and Urbact capacity building activities | All PPs |  | 6 | 510 | 25.5 | 2300 |  |  |  | 2835.5 | 6 | 510 | 25.5 | 2300 |  |  |  | 2835.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2 | Transnational communication |  |  | 17 | 1445 | 72.25 | 0 |  | 0 | 0 | 1517.25 | 7 | 595 | 29.75 | 0 |  | 0 | 0 | 624.75 | 1 | 85 | 4.25 | 0 |  | 0 | 0 | 89.25 | 9 | 765 | 38.25 | 0 |  | 0 | 0 | 803.25 | OK
2.2.1 | Detailed Communication Plan and visual identity | LP/LE | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.2 | Network acronym, tagline, boilerplate | LP/LE | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.3 | A3 poster (?) | LP/LE | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.4 | Setting up online presence (mini site + 1 social media) | LP/LE | All PPs | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.5 | Editing the project website | LP/LE | All PPs | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.6 | Network Articles | LE | All PPs | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.7 | Network Results Product | LP/LE | All PPs | 3 | 255 | 12.75 |  |  |  |  | 267.75 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 255 | 12.75 |  |  |  |  | 267.75 | OK
2.2.8 | Final Conference |  | All PPs | 6 | 510 | 25.5 |  |  |  |  | 535.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 6 | 510 | 25.5 |  |  |  |  | 535.5 | OK
2.2.9 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.10 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.11 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.12 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.13 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.14 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
2.2.15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 104 | 8840 | 442 | 11750 |  | 10750 | 0 | 31782 | 36 | 3060 | 153 | 6000 |  | 1900 | 0 | 11113 | 30 | 2550 | 127.5 | 2100 |  | 2100 | 0 | 6877.5 | 38 | 3230 | 161.5 | 3650 |  | 6750 | 0 | 13791.5 | OK
WP3 | LOCAL ACTIVITIES |  |  | 0 | [31 empty] | OK
3.1 | Operation of the ULG |  |  | 22 | 1870 | 93.5 | 0 |  | 2400 | 0 | 4363.5 | 14 | 1190 | 59.5 | 0 |  | 0 | 0 | 1249.5 | 4 | 340 | 17 | 0 |  | 1200 | 0 | 1557 | 4 | 340 | 17 | 0 |  | 1200 | 0 | 1557 | OK
3.1.1 | Setting up the ULG | All PPs | LE/LP | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.2 | Team building session to the ULG (after kick-offs) | All PPs | LE/LP | 3 | 255 | 12.75 |  |  |  |  | 267.75 | 3 | 255 | 12.75 |  |  |  |  | 267.75 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.3 | Selecting ULG Coordinators | All PPs | LE/LP | 1 | 85 | 4.25 |  | Ext. Meeting Organisation | 1200 |  | 1289.25 | 1 | 85 | 4.25 |  | Ext. Meeting Organisation |  |  | 89.25 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 |  | 0 | 0 |  | Ext. Meeting Organisation | 600 |  | 600 | OK
3.1.4 | Interactive ULG meetings | All PPs | LE/LP | 8 | 680 | 34 |  | Ext. Meeting Organisation | 1200 |  | 1914 |  | 0 | 0 |  | Ext. Meeting Organisation |  |  | 0 | 4 | 340 | 17 |  | Ext. Meeting Organisation | 600 |  | 957 | 4 | 340 | 17 |  | Ext. Meeting Organisation | 600 |  | 957 | OK
3.1.5 | Learning Needs formulated | All PPs | LE/LP | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.6 | Learning Grids created | All PPs | LE/LP | 2 | 170 | 8.5 |  |  |  |  | 178.5 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.7 | Learning Log | All PPs | LE/LP | 4 | 340 | 17 |  |  |  |  | 357 | 4 | 340 | 17 |  |  |  |  | 357 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.1.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2 | Small Scale Actions |  |  | 4 | 340 | 17 | 0 |  | 6000 | 2000 | 8357 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 340 | 17 | 0 |  | 0 | 0 | 357 | 0 | 0 | 0 | 0 |  | 6000 | 2000 | 8000 | OK
3.2.1 | Preparation of SSAs | All PPs | LE/LP | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 | 2 | 170 | 8.5 |  |  |  |  | 178.5 |  | 0 | 0 |  |  |  |  | 0 | OK
3.2.2 | Elaboration of SSAs | All PPs | LE/LP | 2 | 170 | 8.5 |  | Ext. Project Coordination | 6000 | 2000 | 8178.5 |  | 0 | 0 |  | Ext. Project Coordination |  |  | 0 | 2 | 170 | 8.5 |  | Ext. Project Coordination |  |  | 178.5 |  | 0 | 0 |  | Ext. Project Coordination | 6000 | 2000 | 8000 | OK
3.2.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3 | Preparation of the Integrated Action Plans |  |  | 10 | 850 | 42.5 | 0 |  | 0 | 0 | 892.5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 | 425 | 21.25 | 0 |  | 0 | 0 | 446.25 | 5 | 425 | 21.25 | 0 |  | 0 | 0 | 446.25 | OK
3.3.1 | Draft IAP | All PPs | LE/LP | 5 | 425 | 21.25 |  |  |  |  | 446.25 |  | 0 | 0 |  |  |  |  | 0 | 5 | 425 | 21.25 |  |  |  |  | 446.25 |  | 0 | 0 |  |  |  |  | 0 | OK
3.3.2 | Final IAP (incl. Translation to national language(s), if needed) | All PPs | LE/LP | 5 | 425 | 21.25 |  |  |  |  | 446.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 5 | 425 | 21.25 |  |  |  |  | 446.25 | OK
3.3.3 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4 | Local level communication |  |  | 12 | 1020 | 51 | 0 |  | 1000 | 0 | 2071 | 3.2 | 272 | 13.6 | 0 |  | 0 | 0 | 285.6 | 2.4 | 204 | 10.2 | 0 |  | 500 | 0 | 714.2 | 6.4 | 544 | 27.2 | 0 |  | 500 | 0 | 1071.2 | OK
3.4.1 | Creating local visual identity (logo, boilerplate, acronym, tagline, poster) | All PPs | LP | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.2 | Setting up online presence (social media) | All PPs | LP | 1 | 85 | 4.25 |  |  |  |  | 89.25 | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.3 | Regular updates on online platforms (institutional websites, mini site, social media accounts) | All PPs | LP | 6 | 510 | 25.5 |  |  |  |  | 535.5 | 1.2 | 102 | 5.1 |  |  |  |  | 107.1 | 2.4 | 204 | 10.2 |  |  |  |  | 214.2 | 2.4 | 204 | 10.2 |  |  |  |  | 214.2 | OK
3.4.4 | Videos from staff exchanges | All PPs | LP | 0 | 0 | 0 |  | Ext. Communication | 1000 |  | 1000 |  | 0 | 0 |  | Ext. Communication |  |  | 0 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 |  | 0 | 0 |  | Ext. Communication | 500 |  | 500 | OK
3.4.5 | Networking at national level and synergies with other projects | All PPs | LP | 1 | 85 | 4.25 |  |  |  |  | 89.25 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 1 | 85 | 4.25 |  |  |  |  | 89.25 | OK
3.4.6 | Local IAP dissemination events | All PPs | LP | 3 | 255 | 12.75 |  |  |  |  | 267.75 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | 3 | 255 | 12.75 |  |  |  |  | 267.75 | OK
3.4.7 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
3.4.8 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  |  |  |  | 0 | OK
|  |  |  | 48 | 4080 | 204 | 0 |  | 9400 | 2000 | 15684 | 17.2 | 1462 | 73.1 | 0 |  | 0 | 0 | 1535.1 | 15.4 | 1309 | 65.45 | 0 |  | 1700 | 0 | 3074.45 | 15.4 | 1309 | 65.45 | 0 |  | 7700 | 2000 | 11074.45 | OK
|  |  |  | 173 | 14705 | 735.25 | 11750 |  | 20150 | 2000 | 49340.25 | 173 | 5117 | 255.85 | 6000 |  | 1900 | 0 | 13272.85 | 20760 | 4369 | 218.45 | 2100 |  | 3800 | 0 | 10487.45 | 0 | 5219 | 260.95 | 3650 |  | 14450 | 2000 | 25579.95 | OK
BUDGET PER BUDGET LINE PER YEAR
| BUDGET CATEGORY | BUDGET LINES |  | FORECAST BUDGET | BUDGET 2023 | BUDGET 2024 | BUDGET 2025 |  | CHECK
| Staff costs | Staff Costs |  | 14705 | 5117 | 4369 | 5219 |  | OK
|  | Total |  | 14705 | 5117 | 4369 | 5219 |  | OK
| Office and Admin | Office and Administration |  | 735.25 | 255.85 | 218.45 | 260.95 |  | OK
|  | Total |  | 735.25 | 255.85 | 218.45 | 260.95 |  | OK
| Travel & Accommod. | Staff Travel and Accommodation |  | 11750 | 6000 | 2100 | 3650 |  | OK
|  | Total |  | 11750 | 6000 | 2100 | 3650 |  | OK
| External Expertise and Services | Ext. Project Coordination |  | 6000 | 0 | 0 | 6000 |  | OK
|  | Ext. Meeting Organisation |  | 6400 | 0 | 1200 | 5200 |  | OK
|  | Ext. Communication |  | 1000 | 0 | 500 | 500 |  | OK
|  | Exp. & non-staff Travel |  | 6750 | 1900 | 2100 | 2750 |  | OK
|  | First Level Control |  | 0 | 0 | 0 | 0 |  | OK
|  | Total |  | 20150 | 1900 | 3800 | 14450 |  | OK
| Equipment | Equipment |  | 2000 | 0 | 0 | 2000 |  | OK
|  | Total |  | 2000 | 0 | 0 | 2000 |  | OK
| TOTAL |  |  | 49340.25 | 13272.85 | 10487.45 | 25579.95 |  | OK
49340.25
|  |  | CHECK | OK | OK | OK | OK

## AUX (hidden)
External Expertise and Services | Regional development level | ERDF | Nat. co-fin
Ext. Project Coordination | More developed | 65% | 35%
Ext. Meeting Organisation | Transition region | 70% | 30%
Ext. Communication | Less developed | 80% | 20%
Exp. & non-staff Travel | IPA | 95% | 5%
First Level Control